# Collicity — Technical Design (Draft v0.4)

Oct 10, 2026 · Draft for engineering review · Companion to Collicity — Product Specification (Draft v0.18)

# 1. Overview

This document turns the product specification (v0.18) into a system that can be built. It sets out:

- the stack;

- the architecture;

- the designs that keep the five product invariants true by construction;

- a work-package plan through the Enterprise beta (gates 0 and 1).

GA and Home are outlined at coarser grain. Requirement IDs refer to the specification.

Decisions this document assumes (2026-10-05)

| Decision | Choice | Consequence |
| --- | --- | --- |
| Cloud | AWS; one region for the beta, chosen by where the design partners need their data | Managed services throughout; US and EU cells at GA |
| Team | Collicity is one person today; two engineers join within about three months, making three (spec §21) | Three services and one sandbox. Buy everything that isn't the product; defer whatever the beta matrix doesn't require. §14.3 gives the schedule at one engineer and at three |
| Scope | The spec's §18 Beta column names 98 requirement IDs: 96 required, plus ASG‑16 and ASG‑24 for the optional mandate pilot (82 at spec v0.5). GA and Home are outlined | Every Beta requirement maps to a work package (§14) |
| Master rules | The beta runs under the master rules' v0.7 wording. Anything the spec marks pending MR review isn't built until an outside reviewer re-confirms its amendment, and anything postponed isn't built at all (§1.1) | The beta differs from GA in approval validity, compensations, disclosure and more; §1.1 lists each |
| Target date | Design partners live by 2027-12-31; gate 1 by about 2028-03-31 (spec §21) | The three-engineer plan, allowing for hiring time and a 25% contingency; re-baselined after the spikes (§14.3) |

Design principles

- Invariants hold by structure, not by care. Each invariant is enforced by something a bug in ordinary code can't bypass: an IAM role, a database role, a network tier, or the single code path every call must take.

- One enforcement point. Every external call leaves through the gateway, which alone holds credentials and alone can reach the internet. That covers target systems, model providers and sandbox compute.

- Models propose; code decides. Models return structured proposals. Only deterministic code changes state, and a side effect runs only against an approval that matches it exactly.

- Postgres is the system of record. Run state, approvals, budgets, the audit log and the outbox live in one database. Temporal executes short segments and holds nothing it can't lose.

- Buy what isn't the product. Identity, durable execution, hosting, observability and compliance tooling are bought. The gateway, run engine, ledger, intake and untrusted-content library are built.

## 1.1 Master rules in the design

Each master rule (spec §1) is enforced by something in this design, never by a model. The last column says how the rule applies in the beta, which runs under the v0.7 wording, and what is pending MR review: not built until an outside reviewer re-confirms the amendment. The one exception is the optional mandate pilot (P1.11), which can start once MR‑09 and MR‑11 are re-confirmed and the rest of spec §18.1's conditions hold.

| Rule | Where the design enforces it | Beta, and pending MR review |
| --- | --- | --- |
| MR‑01 | A 401 or 403 ends the step with no retry; a CAE claims challenge moves the run to Paused: re-authorization; consent binds the upstream account to the signed-in person (§5.1, §5.3) | In force |
| MR‑02 | Grant evaluator and response filter at the gateway; the broker releases only the user's own token (§5.1–5.3) | Personal credentials only. Pending: the service-account exception (CON‑05) and directory polling (CON‑06, §5.6) |
| MR‑03 | KMS envelope encryption; only the gateway's role decrypts; canary scanning of prompts, logs and stores (§2, §3.1, §15) | In force |
| MR‑04 | Every assignment and instance has an agent_id, carried on runs and audit records (§10, §12); the alpha signature adds a verifiable Collicity identity (§5.7) | In force |
| MR‑05 | Egress only to hosts in approved manifests (Network Firewall); recipient rules; disclosure screens for snapshots (§3.1, §5.2, §9) | In force. Outside the tenant, the beta sends only snapshots to outside recipients, after a disclosure-screen approval and only for labels that allow it, and alerts to destinations an admin configured |
| MR‑06 | Typed grants with resource selectors and field allowlists, enforced before the call and on the response (§5.2) | In force |
| MR‑07 | Router eligibility includes region, retention and the compliance profile; no cross-region inference (§7.1) | In force |
| MR‑08 | Lineage carries labels; every beta output takes the tenant's most restrictive label (§8.2) | Default label in the beta |
| MR‑09 | Canonical approval hash, validity checked at consumption, effect journal (§3.2, §5.1, §5.4) | 15-minute validity; every compensation has its own approval. Pending: tiered validity, mandates, compensations under the original authorization |
| MR‑10 | No purchases in the beta; Home's purchase ledger and approvals (§14.5) | Pending: purchase mandates (PAY‑03) and price ceilings (PAY‑05) |
| MR‑11 | One record per approved action, batches included; phishing-resistant authentication; approver authority checks (§5.4, §5.8, §5.9) | In force; batch approval after its self-review. Pending: mandates, device-signed and offline approvals |
| MR‑12 | The approval screen renders the canonical action; dry runs (§3.2, §4.4) | In force |
| MR‑13 | untrusted normalization, lineage taint, quarantined reading, injection screening (§7.4, §8) | In force |
| MR‑14 | Standing instructions are read-only to worker; only accept_version() changes them; Collicity's own API is never a connector (§8.2) | In force |
| MR‑15 | Graph subscriptions exist only for triggers an accepted version declares; any other persistent-rule action needs approval (§11) | In force |
| MR‑16 | Write-ahead audit of every connector call, model call, data access, approval and kill-switch use, hash-chained (§10) | In force |
| MR‑17 | AI disclosure on everything Collicity sends; beta reply drafts carry a visible note and a header (§5.5) | Visible note. Pending: header-only disclosure on drafts the user sends |
| MR‑18 | A fixed User-Agent, the act claim, no retry that changes identity (§5.1, §5.3); the alpha signature (§5.7) | In force |
| MR‑19 | Status is computed from run state, the effect journal and evidence, never from model text (§4.1) | In force |
| MR‑20 | Ledger reservations, volume counters, rate limits, hard timeouts (§5.1, §6) | In force |
| MR‑21 | Epochs stop calls within seconds; a pause stops compensations too; in the beta a cancel rolls back only through approved compensations (§4.1) | In force |
| MR‑22 | Only triggers and admission create runs; child workflows reuse the parent's grants (§4.1) | In force |
| MR‑23 | A denial ends the step; the supervisor escalates; screening compares tool calls with the plan (§5.1, §7.2, §7.4) | In force |
| MR‑24 | extract parses without executing anything; no model-written code or queries run (§8.1) | In force. Postponed: sandboxed model-written code and queries; browser automation is out of v1 |
| MR‑25 | The audit log is INSERT-only; manifests can't declare logging or monitoring changes; the security class is refused (§5.2, §10) | No security or access changes. Pending: approved changes, with two approvers to widen access |
| MR‑26 | The compliance profile constrains eligibility and connectors; a step stops before the call when no compliant path exists (§7.1) | In force |

# 2. Stack

Spec v0.4's stack defaults came from the archived compliance-assistant plan v3. Most stay. Several change because something fits a three-person team on AWS better, and several are deferred because the beta doesn't need them. Spec v0.5 adopts these decisions (§5, §16).

| Layer | Default in spec v0.4 | Decision | Reason |
| --- | --- | --- | --- |
| Compute | Kubernetes + Terraform | Change: ECS on Fargate + Terraform; EKS Auto Mode only if self-hosted delivery is ever needed | Three services don't justify running a cluster. Per-task IAM roles and security groups are the trust boundaries |
| Untrusted-code sandbox | WASM or microVM (CON‑14) | Decide: Firecracker microVMs. Beta: a Lambda with no internet access (an S3 endpoint only) for content extraction. GA: Fargate tasks behind a proxy that injects credentials on the way out, for custom connectors. Model-written code and queries, and browser automation, are postponed (SEC‑15); nothing here builds them | Managed isolation without running gVisor. The connector SDKs are TypeScript and Python, which WASM serves poorly |
| Backend | Python 3.12, FastAPI, Pydantic v2 | Keep, on Python 3.13 (3.14 during GA), with SQLAlchemy 2, psycopg 3 and Alembic; no PgBouncer in the beta | Strongest ecosystem for model SDKs, document parsing and statistics. Pydantic models double as structured-output schemas. 3.13 is supported to October 2029 |
| Orchestrator | Temporal | Keep: Temporal Cloud over AWS PrivateLink, running short run segments (§4). DBOS is the fallback | Nothing to operate. Short segments remove workflow-versioning risk and dual writes |
| Database | PostgreSQL 16 with RLS | Change: Aurora PostgreSQL on the newest major version Aurora supports (17; 18 once available), Serverless v2 outside production; RLS as SEC‑09 specifies | Commits are durable across three Availability Zones, which gives the audit log RPO 0 if a zone fails |
| Live updates | Postgres outbox + Redis 7 | Change for the beta: no message broker. The outbox feeds Server-Sent Events, with Postgres LISTEN/NOTIFY as the wake-up. Valkey (ElastiCache Serverless) at GA if load needs it | One fewer system; SSE's Last-Event-ID is the outbox sequence |
| Object storage | S3-compatible | Keep: S3 with SSE-KMS under the tenant's content key (each write names it; S3 Bucket Keys limit KMS calls); Object Lock (compliance mode) for audit anchors | — |
| Vector store | pgvector or dedicated | Defer to GA (pgvector) | Beta retrieval is live federated search with the user's token (CON‑09) |
| Policy engine | Cedar or OPA (CON‑02) | Change: in the beta, a typed, deterministic grant evaluator in the gateway. Cedar arrives at GA with policies as code (ADM‑08), custom connectors (CON‑15) and the edge executor, tested against the beta evaluator on the same cases | The beta's grants are a small, closed rule set; property-based tests prove it more directly than policies would |
| Secrets vault | KMS/HSM-backed vault (CON‑04) | Decide: KMS envelope encryption with ciphertexts in a vault schema. A KMS key per tenant for each purpose that holds tenant data (SEC‑01): credential (the vault: connector tokens, CON‑05 credentials and BYO provider keys), audit (wraps per-person keys and encrypts the tenant's audit archives) and content (S3 snapshots, payloads, prompts and outputs). The tenant is also in the encryption context. KMS rotates these keys automatically; customer-managed keys at GA (XKS or CloudHSM) rotate under the customer's control. Aurora is encrypted under its cluster key, and rows are isolated by row-level security (SEC‑09; spec §21 asks whether rows need tenant keys too). Secrets Manager for service secrets; XKS or CloudHSM for customer-managed keys at GA | No Vault cluster to run. Per-tenant keys make customer-managed keys a key swap at GA for the data they cover. Per-person audit keys (SEC‑07) are wrapped data keys, not 100,000 KMS keys |
| Sign-in | Hosted OIDC/SAML service | Decide: WorkOS for SSO, Directory Sync (SCIM) and its Admin Portal; AuthKit for consumer sign-in and passkeys in Home. Approvals and step-up need phishing-resistant authentication (CON‑21, §5.8) | Enterprise SSO and SCIM are beta-critical and commodity |
| Connector authorization | — | Decide: the token broker runs its own OAuth 2.1 consent per connector (authorization code with PKCE). The Entra application authenticates with client assertions signed by a KMS key that can't be exported. MSAL is configured for continuous access evaluation (CAE) | Sign-in tokens can't be exchanged for on-behalf-of tokens. Collicity's own application credential never leaves the HSM |
| Model providers | One hosted provider + bring-your-own | Decide: Claude through Claude Platform on AWS, signed with SigV4 from the gateway's task role, so no static key exists; token counting, Batches and inference_geo are available. A second model family on Bedrock judges across families, chosen by evaluation | Invariant 3 holds for the default provider by construction, with full Claude API parity inside AWS |
| LLM interface | — | Decide: a thin in-house interface over the official SDKs | Per-call reservations (BUD‑03), decision records (RTR‑04) and cache salting need control of every call |
| Internal connector protocol | Exposed internally as MCP (§6.1) | Change: in the beta, connectors are in-process adapters with MCP-shaped tool schemas. The MCP transport arrives at GA with remote and custom connectors and the desktop | One fewer network hop for first-party code. Grants, approvals and idempotency keys need first-class fields |
| Web | React + TypeScript | Keep: React 19 as a Vite single-page app on CloudFront, with TanStack Router and Query and React Aria Components. The manual builder is an outline editor, not a canvas | Accessible by default (PLT‑06). A canvas costs weeks and is hard to make work with a keyboard or screen reader |
| Desktop | Tauri 2 | Keep, decide at Phase 2 after a one-week spike on WebKitGTK and screen readers; Electron is the fallback | The local-connector sandbox is a Rust sidecar under either shell |
| Mobile | React Native / Expo (open, §21) | Decide: Expo, with custom native modules for HomeKit, App Intents and approvals signed with a device key | Mature background geofencing, actionable push and biometrics |
| Observability | OpenTelemetry | Keep: OpenTelemetry through the AWS Distro for OpenTelemetry (ADOT) to CloudWatch and X-Ray over VPC endpoints. GenAI spans carry no prompt or response content. Sentry in the browser only; PostHog with identifiers only | Works from the worker's no-internet tier, with the fewest vendors |
| Agent request signing | Web Bot Auth (spec §6.4, alpha) | Decide: Ed25519 signing in the gateway's HTTP client; key custody is an open choice (§5.7) | One enforcement point already sees every outbound request |
| Tooling | — | pnpm, uv, just, GitHub Actions, Semgrep, Dependabot, Syft, cosign. Turborepo and Cargo deferred | — |

Model defaults. Prices are per million input / output tokens and live in the price catalog (BUD‑08), not in code.

| Use | Default | Price | Note |
| --- | --- | --- | --- |
| Triage, classification | Claude Haiku 4.5 | $1 / $5 | — |
| Extraction, drafting, tool use | Claude Sonnet 5.5 | $2 / $10 | — |
| Take-over (SUP‑03), high criticality | Claude Opus 5.5 | $4 / $20 | Effort set explicitly per task |
| Grounded and subjective judging (SUP‑02) | A non-Anthropic family on Bedrock | Catalog | Chosen on the labeled set in spike S7 |
| Excluded under zero data retention | Claude Fable 5.1 | $10 / $50 | Requires 30-day retention, so RTR‑01 excludes it for tenants that require zero data retention (PRV‑05) |

A refusal (stop_reason: refusal) counts as a failed attempt for that model (INV‑07), and the router re-routes under a new reservation. Server-side automatic fallbacks stay off: they could pick a model outside the tenant's allow-list or reservation.

# 3. Architecture

Clients never call target systems or model providers. Everything leaves through the gateway, the one service that holds credentials and can reach the internet. The services that touch untrusted content hold no credentials.

## 3.1 Deployables

| Unit | Runs | Privileges and reach | Why it's separate |
| --- | --- | --- | --- |
| app | ECS behind ALB and WAF: REST API (OpenAPI), Server-Sent Events, Graph and WorkOS webhooks, admin console, Q&A, builder | Database role app_user with tenant and visibility RLS; egress to WorkOS and SES only | It serves people, so it can never read past what each person may see (SEC‑08). Q&A prompts are assembled under the asker's RLS |
| worker | ECS in a subnet with no NAT: Temporal run segments and intake, outbox relay, notifier, audit sealer, sweepers, retention jobs | app_worker: tenant RLS, read-only on standing-instruction tables. Temporal over PrivateLink; AWS services over VPC endpoints | Untrusted data is handled and prompts are assembled with no tokens, no model access and no internet (invariants 3 and 5; SEC‑12) |
| gateway | ECS behind NAT and an AWS Network Firewall domain allowlist: connector adapters, token broker, grant evaluator, approval verifier (§5.8, §5.9), request signer (alpha, §5.7), model adapter, compute adapter, write-ahead audit | gw: the only role that can decrypt token keys with KMS, invoke Claude Platform on AWS, Bedrock and extract, or reach the internet | The single structural enforcement point for invariants 1–4 |
| extract | Lambda in a VPC with no internet route, S3 gateway endpoint only | None | The CON‑10 sandbox. Only the gateway invokes it, after reserving its compute (BUD‑03) |

Static assets are served from S3 through CloudFront. Temporal Cloud stores only identifiers, enums and error codes (§4.1), encoded with one platform KMS key, since Temporal holds no tenant content.

Network tiers

- Public ingress: CloudFront, and the ALB with WAF.

- Restricted egress: app reaches WorkOS and SES only. gateway goes out through the Network Firewall allowlist of declared hosts, which CON‑12 manifests list.

- No egress: worker and extract.

- Key directory: the Web Bot Auth key directory is static content served through CloudFront on its own hostname (§5.7).

Hardening at GA

- Split the token broker out of gateway into its own service.

- Add Valkey if live-update fan-out needs it.

- Add the EU cell; identifiers and hostnames are region-aware from day one.

- Add the Rust edge executor for the desktop and the on-prem relay.

- Add Cedar.

- Add dedicated worker pools for Enterprise tenants that require them (the spec's per-tenant execution workers, P1).

## 3.2 Request paths

Model call (invariants 3 and 4)

- The caller (worker, or app for Q&A) reserves the worst case against every applicable ledger account in one transaction (BUD‑10) and passes the reservation ID.

- The gateway recomputes the worst case itself from the recorded price version:

  - input tokens, counted by the provider's token-counting endpoint, × the input price;

  - plus the cache-write premium on the cached span (an extra 0.25× for a 5-minute write, 1× for a 1-hour write);

  - plus max_tokens × the output price;

  - plus per-use tool fees.

It refuses any reservation smaller than its own figure.

- It re-checks RTR‑01 eligibility (admin allow-list, classification label, residency, retention terms) and scans the prompt for fingerprints of live tokens and for honeytokens.

- It prepends a cache salt, HMAC(tenant, visibility set). Provider caches are scoped to Collicity's own workspace or organization, not to a tenant, so the salt keeps cached prefixes from ever matching across visibility groups (SEC‑08).

- It marks the reservation started, calls the provider, and settles to the actual cost from the response's usage.

Read call (invariants 1, 4 and 5)

- The worker presents an opaque step grant. It is a database row for one step and attempt (CON‑04), valid only while the tenant, user, assignment and run epochs it recorded are current.

- The gateway re-checks the user, the session and the connector (CON‑06). It validates parameters against the pinned manifest, resolves resource parameters to stable IDs, and evaluates the capability grant (§5.2). A paid action also needs the caller's reservation (§5.1, BUD‑03).

- The broker supplies the user's token, and the adapter calls the target with the CON‑07 User-Agent and, while the alpha is on, a Web Bot Auth signature (§5.7).

- The response is filtered to granted resources and fields and stored in S3 under its data class. It comes back to the worker as a content handle carrying its source IDs and an untrusted taint (§8.2). An audit record is written.

Write action (invariants 1, 2, 4 and 5)

- A model drafts a structured proposal. Before it is stored, deterministic checks run:

  - the schema;

  - citation integrity: the cited passage exists, matches the snapshot, and isn't hidden-only;

  - a capability pre-check;

  - the target's current value.

- The proposal becomes an approval request. Its canonical hash (JSON Canonicalization Scheme, RFC 8785) binds the action, the resource IDs, the parameters, the item's base revision, the target's version and the declared compensation (§5.4). The request expires after 7 days (RUN‑04).

- A person approves, alone or in a batch (§5.4), with phishing-resistant authentication (CON‑21, §5.8). The approver must pass the item's visibility check (SEC‑08) and the approver authority check (ASG‑25, §5.9).

- An action run calls the gateway. In one transaction, the gateway:

  - consumes the approval, checking that it is still valid (in the beta, decided less than 15 minutes ago with no wait or pause since; RUN‑04). A compensation always checks that the original effect was applied and not yet reversed, and restores only the recorded values. In the beta it also consumes its own approval; after MR review it runs under the original authorization (§5.4);

  - inserts the effect row with a unique idempotency key;

  - increments the volume counter (compensations don't count) and marks a paid action's reservation started;

  - writes the audit intent record.

Only then does the broker release the token.

- The call proceeds according to the action's duplicate-prevention class (RUN‑07). Then the audit result and the effect outcome are recorded, including the target version read back.

Mail to runs (§11)

- A Graph change notification wakes the intake workflow of each assignment or instance that watches the scope; each reads the per-folder delta under its owner's token (CON‑01), using immutable IDs.

- Capture follows the archived compliance plan v3.1 §7: snapshot bytes to S3, then one transaction for the source rows and outbox events, then advance the checkpoint.

- The gateway invokes extract to normalize the content (CON‑10).

- A trigger evaluator that reads only headers, and so costs no model calls, resolves sender identity (ASG‑15) and applies the per-sender counter (ASG‑17).

- Trigger deduplication (RUN‑02) and admission (RUN‑01) start one intake run per email.

# 4. Runtime

Postgres owns every run's state. Temporal executes short segments between waits, so no workflow stays alive across a human decision, a pause or a deploy.

## 4.1 Runs and segments

- State. run.state, state_version and continuation change only through transition(), which checks the version and writes outbox events in the same transaction. The §7.6 states map one to one; terminal outcomes follow RUN‑06.

- Segments. A segment is a Temporal workflow with the ID run:{id}:{n}: a thin, deterministic loop that calls next_step and execute_step activities.

  - Parallel branches and for-each loops run as child workflows, up to 50 items per child.

  - The task graph is interpreted inside activities, so most code changes never touch workflow replay. CI replays recorded histories to catch the rest.

- Waits end segments.

  - Entering a Waiting or Paused state commits the continuation and ends the segment.

  - A decision, resume or re-authorization commits segment n+1 together with an outbox event, and the relay starts it. The workflow ID makes the start idempotent.

  - Completed steps never re-run, and the next step always gets a fresh token and a new reservation (RUN‑04).

- Timers. One sweeper, a Temporal Schedule running every 30 seconds, scans indexed deadlines:

  - approval expiry at 7 days, and decided-approval validity (15 minutes in the beta);

  - ASG‑10 reminders and escalation;

  - pauses older than 14 days, which take the cancel path;

  - unsettled reservations;

  - INV‑06 outcome windows.

- Kill switch (ASG‑13). Pausing a run, a user's runs or all runs bumps the run, user or tenant epoch. The gateway refuses new calls for that scope within seconds, and any live segment is cancelled; thousands of workflows never need a signal. A pause stops every call, compensations included. A cancel stops forward work; in the beta, a run with applied effects then offers each compensation for approval (RUN‑06), and whoever cancelled can stop that rollback (ASG‑13). Suspending a user is different: it deprovisions them (§5.6).

- Honest status (RUN‑08). Run, step and queue status is computed from run.state, the effect journal and evidence records. Model text never sets a status.

- No spawning (RUN‑09). Only triggers and admission create runs; activities have no API that creates runs, assignments or triggers. Child workflows for branches and for-each items reuse the parent's step grants. Arming a trigger the version declares is an action with its own approval.

- Temporal payloads. Only identifiers, enums and error codes. Inputs, outputs and prompts are claim-checked: stored in S3 under their data class (spec §15) and referenced by ID.

## 4.2 Email triage as runs

- Intake run, one per email: triage → extract the requested items with citations → find the targets through gateway reads → draft action proposals → supervisor checks (§7.2) → persist queue items and approval requests. The run ends there, so RUN‑01's default of 5 concurrent runs per assignment stays meaningful.

- Action run, one per approved action. Its trigger dedup key is the approval ID, so each approval executes at most once. A batch approval creates one approval record, and so one action run, per action (§5.4). Action runs are admitted ahead of new triggers, within the cap, so their approvals don't lapse while queued (RUN‑01).

- Long human waits live in the work queue. Generic human steps (ASG‑10) use the same park-and-resume mechanism. Inside a parallel branch or a for-each loop, a branch or item that reaches a human step runs as a child run with its own state and segments, so waits still end segments; the parent waits for its children.

## 4.3 Runtime semantics

| Rule | Implementation |
| --- | --- |
| RUN‑01 Overlapping runs | Admission locks assignment_slots. Only Queued and Running runs count against the cap and the queue bound. A run that has executed a step resumes without waiting for a slot; one that paused before its first step returns to Queued in trigger order, and the policy applies to it as to a new trigger. Policies: skip; queue (bounded, first in first out); replace (the older run is cancelled at its next step boundary); concurrent (capped). A run carrying out a decided approval is admitted ahead of new triggers, within the cap |
| RUN‑02 Trigger deduplication | trigger_event.dedup_key is unique, with an expiry. The mail key is (tenant, assignment or instance, mailbox, Graph immutable message ID), never the Message-ID the sender chooses, with a window at least as long as the 90-day monitored window. The same key derives the workflow ID |
| RUN‑03 New versions | Admission resolves the latest or pinned version. A version that isn't accepted and either widens any grant element (§5.2) or raises the budget → Paused: re-acceptance; accepting it returns those runs to Queued in trigger order (RUN‑01). An instance of a shared assignment runs only the version its recipient accepted (ASG‑23) |
| RUN‑04 Credentials after waits | The broker fetches a token on every call. Approvals bind by canonical hash, and an undecided request expires after 7 days (state expired). A decided approval is valid for 15 minutes in the beta, and only until the run next waits or pauses; tiered validity (24 hours, or 1 hour for high-impact actions) and device-signed approvals wait on MR review (§1.1). A change to either base version makes it stale; in a batch, each record goes stale on its own |
| RUN‑05 Revocation mid-run | Epochs are checked on every call. A result that lands after revocation is quarantined and never returned. The run moves to Paused: re-authorization, or takes the cancel path if the user was deprovisioned |
| RUN‑06 Failure and compensation | An effect journal records every applied effect. Retryable steps retry within budget. Otherwise compensations run in reverse order through the gateway, ending Rolled back. In the beta each compensation is an action with its own approval; after MR review it runs under the original authorization (§5.4). Any failed or unapproved compensation, or an irreversible effect, ends Completed with partial side effects, with a repair item |
| RUN‑08 Honest status | Status comes only from recorded state and evidence (§4.1) |
| RUN‑09 No spawning | Only triggers and admission create runs; child workflows reuse the parent's grants (§4.1) |
| RUN‑07 Duplicate prevention | Classes (a) and (b) retry safely. Class (c) waits out the declared read-after-write lag, finds the object by correlation ID, then retries or records the result. Class (d) never retries: Paused: outcome unknown, with a repair item |

If an owner is deprovisioned after effects were applied, there is no delegated token left to compensate with. The run ends Completed with partial side effects, and its open repair items go to a custodian the tenant designates (RUN‑06). A custodian's repair item rests only on the applied effects and their target resources, not on the run's sources, so it stays within SEC‑08: the custodian sees it if they can read those targets. For an outcome-unknown write, the item shows only the action, target, account, attempt time and correlation ID. Items no custodian can see are flagged to tenant admins with identifiers only (RUN‑06).

## 4.4 Versions and the builder

- Immutable versions (ASG‑01). Assignments and tasks are versioned. A version is accepted only through accept_version() (§8.2). The acceptance screen shows the widening diff and the provenance of every standing instruction.

- Manual builder (ASG‑04). An outline editor with steps, branches, parallel blocks and for-each blocks. Task forms cover the description, capability grants (with resource pickers backed by gateway reads), the model or "Auto", success criteria, approval gate, timeout and retry.

- "Write this for me" and "Improve" (ASG‑02) draft a description that the person must accept. They are charged to the person's workspace budget (BUD‑11, §6.1).

- Dry run (ASG‑05) runs the version with read-only grants. Write capabilities are stripped before step grants are issued. It reports what would happen and its real token cost.

- Success criteria (ASG‑06) are chosen from the typed check library (§7.2) with parameters. Free-text criteria become subjective checks for the judge.

## 4.5 Sharing (GA)

Spec §7.7 gives two ways to share, and neither lends anyone the owner's access. In the beta, reports are shared as one-off snapshots; assignment sharing and recurring report sharing arrive at GA.

- Report sharing (ASG‑19) reuses snapshots (SEC‑10). A report_share row holds the assignment version, any publishing mandate (mandate_id), the recipients (people or groups), the source scopes and label ceiling the owner confirmed, and a state (active, held, withdrawn). For each new edition, a publish activity checks:

  - the edition comes from the confirmed version, and every source in its lineage lies within the confirmed scopes;

  - its label is no higher than the confirmed edition's and needs no second approver;

  - the supervisor didn't flag it and SEC‑13 screening found nothing;

  - each recipient, including each current group member, meets SEC‑10's recipient rules;

  - the owner can still read every source and holds the Publisher permission.

Each edition then waits for the owner's approval, unless a publishing mandate (ASG‑24, after MR review) covers it and all of these hold; editions for recipients outside the tenant are always approved one by one. If a check fails, the edition is held and the owner is asked again; if the owner has lost access to a source, nothing publishes until they regain it.

- Instances (ASG‑20). Sharing with named people creates an assignment_instance for each; a group or tenant share creates one only when a member opens the offer, with SCIM group events driving joins and leaves.

  - Each instance has its recipient as owner and a state: offered, blocked (something missing), active, or ended with a reason (withdrawn, declined, left, archived).

  - It records the version its recipient accepted and any newer version on offer, its own resolutions of personal selectors, its triggers (mail triggers on the recipient's resolved folders; webhook triggers with their own endpoint, verified by the sender's signature or by a secret the sender's system generates and the recipient enters into the vault, so Collicity never displays one (MR‑03; §18) and an assignment budget under the recipient's user budget.

  - Admission (RUN‑01) starts runs only for an active instance, on its accepted version. Every run, approval, step grant and audit record carries the instance owner, so the gateway always sees the recipient as the principal. A mandate (pending MR review) applies only to the instance it was made for.

- Acceptance and versions (ASG‑23). accept_version() records acceptance per instance, by its owner only. A new version is recorded as an offer and changes nothing until the recipient accepts it on a screen that shows the diff of instructions, capabilities and provenance against the version the recipient last accepted, never against the previous published version; a version that widens anything beyond the accepted version re-runs the whole precheck first. The acceptance screen hides the names of resources and sources the recipient can't read, and the share screen shows the owner what recipients will see.

- Access precheck (ASG‑21) has two stages.

  - At share time, Collicity checks its own records for each recipient: role, admin policy for each connector and action, model eligibility (the pinned model or, on Auto, the curated default, against the recipient's own policy and configured providers) and budget headroom.

  - When the recipient opens the share, they connect any missing connector. Each connector's access check then runs under the recipient's own token and reads only their access to the declared resources; for Graph, that is a metadata read of each resource as the recipient, and write access is verified where the target offers an effective-permission check and is otherwise unverifiable.

  - Results are stored per requirement with the principal that ran them, always the recipient, and shown to the owner only for resources the owner can read. A denied check is recorded as a result, never as an out-of-policy call (CON‑03).

  - After acceptance, a dry run the recipient starts settles unverifiable reads, charged to their workspace budget; the instance's triggers start only when it passes.

- Access requests (ASG‑22) are access_request rows: route, recipient, resource, operation, the person it was filed as and approved by, state (open, granted, rejected, expired, stale, withdrawn) and a 7-day expiry.

  - Policy, budget and consent requests stay inside Collicity.

  - An IT-queue ticket runs as a one-step run of a built-in access-request assignment under the requester's identity, with a fixed grant the tenant admin sets (one ticketing connector, one queue, allowlisted fields, a per-person daily limit). It takes the normal write path (§5.1) with the requester's approval of the exact ticket, and is charged to the requester's workspace budget.

  - Collicity never changes a target's permissions. It re-runs the precheck when a grant lands, withdraws requests when a share ends, and tells granters when the access is no longer needed.

- Intake per instance. Each instance's mail trigger has its own intake workflow under its owner's token, and its dedup keys include the instance (RUN‑02). At acceptance, if another instance of the same assignment already watches the same fixed mailbox, the screen says so and offers a delegate role (§18.1) or a report share instead.

- Ending (ASG‑23). Withdrawing a report share stops its editions. Withdrawing an assignment share, a recipient leaving, or the assignment being archived disables the instance's triggers and admission; runs already started finish their current step and end through RUN‑06. Version rows stay while any instance's run is pinned to them. Admins can pause every instance of one assignment through its epoch (ASG‑13).

# 5. Connector gateway

The gateway decides whether a call is inside the permission ceiling before any credential exists for it, and records that decision before anything leaves.

## 5.1 Request path

- Load the step grant. Check that the run is Running, its version is accepted by the run's owner (for an instance, by its recipient), the user is active with current epochs, and the connector is still approved (CON‑06). These are read from Postgres, cached for at most 5 seconds and invalidated by LISTEN.

- Validate parameters against the pinned manifest, and identify the resource and recipient parameters. An action whose resource can't be determined before the call needs approval every time (CON‑02).

- Evaluate the grant (§5.2), denying by default. A denial writes a denied audit record and ends the step. Repeated denials suspend the task and raise a security event (CON‑03). Then check the action's cost model in the pinned manifest (BUD‑03): an action without one is refused, and a paid action needs the caller's reservation, which the gateway checks against its own worst case at the recorded price version and marks started just before the call (inside the step-4 transaction for a write).

  - Check the compliance profile (SEC‑17): the connector, destination host and region, data class and retention. Take a compliant path if one exists; otherwise stop before the call (Waiting: person).

- For a write, one transaction:

  - consume the approval: accepted, still valid under RUN‑04, hash match, unused, decided through a phishing-resistant authentication event by an approver who passed the authority check (§5.4, §5.8, §5.9). A compensation always checks that the original effect was applied and not yet reversed, and restores only the values recorded when the effect ran (RUN‑06, CON‑02). In the beta it also consumes its own approval. After MR review it runs under the original authorization instead, which may already be used or expired (invariant 2);

  - insert the effect row (unique idempotency key);

  - increment the volume counter, only if used + n ≤ limit (compensations don't count, CON‑02);

  - write the audit intent.

- Release the token. The broker unwraps the refresh token with the tenant's credential key and refreshes it with the CAE capability. The access token stays in memory only.

- Make the call.

  - While the alpha is on, the adapter's HTTP client signs the request (CON‑17, §5.7).

  - A 401 or 403 ends the step, with no retry.

  - A CAE claims challenge moves the run to Paused: re-authorization.

  - A timeout or lost acknowledgement is handled by the action's RUN‑07 class.

- Filter and record. The response is filtered to granted resources and fields, the payload goes to S3 with its lineage, and the audit result and effect outcome are written. A paid call's reservation settles to the target's reported charge; if the outcome is unknown (RUN‑07), it stays started and is charged in full (§6.2).

- Revocation bumps an epoch, and new calls stop at once. A call already in flight is logged "completed after revocation" and quarantined (RUN‑05).

## 5.2 Capability grants

The beta evaluator is a pure function over typed values:

(manifest, grant, admin policy, consented scopes, request) → allow | deny(reason)

Each element of CON‑02 has a typed form:

| Element | Typed form | Enforced |
| --- | --- | --- |
| Connector and action | Manifest action ID, pinned manifest version | Before the call |
| Resource selector | Stable IDs resolved at acceptance: drive item and table ID, site and list ID, mail folder ID | Before the call; responses filtered after |
| Field allowlist | Typed read and write sets; each field has a type (number, text, date, choice) | Writes before the call; reads filtered after |
| Recipient rule | original_sender_only resolves to the authenticated From address at medium or high confidence | Before the call; drafts read back after |
| Parameter limits | Bounds per field (e.g., a change of at most 50 units); forbidden operations | Before the call |
| Volume limit | A count per run or per period | Atomic counter in the write transaction |

- Stable IDs. Selectors resolve to the target's immutable identifiers when a version is accepted, so renaming a workbook or folder can never widen a grant. If a fixed selector's resolution changes, that is a new version (RUN‑03). A personal selector resolves per instance when its recipient accepts (ASG‑20), and widens() compares an instance's resolutions only with its own earlier ones.

- Widening. widens(old, new) is a subset check on each element. Any widening needs re-acceptance (RUN‑03, invariant 2).

- Typed writes. Text written to Excel or SharePoint is escaped so it can't become a formula; =WEBSERVICE(…) or =HYPERLINK(…) would send data out. Number fields accept only numbers.

- Impact tier (RUN‑04). impact_tier(action, parameters) returns high when the action is irreversible (its RUN‑06 class), in the CON‑12 destructive class, publishes or sends, is a purchase above the account's threshold, changes more than 10 records, is one of PAY‑08's four actions, or is in the security class; otherwise low. A restorable overwrite is low. The approval screen shows the tier, and batch approval refuses high-impact actions (§5.4).

- Security class (SEC‑16). Manifests declare security and access actions as their own class, and none may change logging or monitoring. In the beta the gateway refuses every action in the class (v0.7 wording).

- Reply drafts. Graph's reply drafts may follow a Reply-To header that the sender controls. The adapter therefore sets toRecipients explicitly from the authenticated From address, and reads the draft back to verify its recipients before recording success. Spike S3 confirms the behavior.

## 5.3 Tokens and attribution

- Consent (CON‑01, CON‑08). Each connector uses OAuth 2.1 authorization code with PKCE, and scopes never exceed the manifest. At consent, the upstream tenant and object IDs (tid, oid) must match the signed-in person's SSO subject, or the connection is rejected; nobody can connect someone else's account.

- Sealing (CON‑04). Refresh tokens are encrypted with KMS envelope encryption (the tenant's credential key, with the tenant also in the encryption context) and stored in the vault schema. Only the gateway's task role can decrypt them (CON‑04). Each refresh seals the new refresh token the identity provider returns and destroys the old ciphertext. Access tokens live in memory, are restricted to their audience, and are never logged. DPoP or mTLS binding is added for targets that support it; none of the beta targets does.

- Attribution (CON‑07). Every call carries User-Agent: Collicity/<version> (agent; run=<run-id>), the act claim where the target supports token exchange, and an audit record naming the user and the agent (the assignment or instance, MR‑04). While the alpha is on, it also carries a Web Bot Auth signature, whose key ID and nonce the audit record keeps (§5.7). Each connector's documentation states what the target's own log will show.

- Systems without OAuth (CON‑05) are built only if a design partner needs them. Personal credentials are sealed the same way. The service-account exception is pending MR review and isn't built (§1.1).

## 5.4 Approvals, batches and compensations

- Validity (RUN‑04). An undecided request expires after 7 days. A decided approval authorizes one execution: in the beta, within 15 minutes of the decision and only until the run next waits or pauses. After MR review, it stays valid while the action hash and the target's base version are unchanged, for up to 24 hours (low-impact) or 1 hour (high-impact). approval_request.valid_until is set when the person decides, and the gateway checks it again at consumption.

- Batch approval (ASG‑11). The approval screen lets a person select several fully shown, low-impact actions and approve them with one gesture, up to 10 records in total; larger sets are split.

  - The gesture creates one decided approval_request per action, each binding its own canonical hash, base versions, compensation and validity. An approval_batch row records the selection and the gesture's authentication event (§5.8).

  - High-impact actions (§5.2) can't be selected into a batch.

  - If one action goes stale, only its record returns for review.

  - Batch approval is a reading of MR‑11 that needs its self-review before it ships (spec §21).

- Compensation. The approval hash covers the action and its declared compensation, with exact restore values (for example, restore Qty to 10).

  - Always: a compensation runs only for an effect this run applied and hasn't reversed, and only restores the values recorded when the effect ran (RUN‑06, CON‑02).

  - In the beta (v0.7 wording), each compensation is also an action with its own approval request (approval_request.kind = compensation, linked to its effect_id), showing the restore values. A compensation that deletes, such as removing a created list item or a reply draft, is high-impact (§5.2), so it is approved on its own, never in a batch, and its approver needs delete permission (§5.9; §18). If no one approves it before its ASG‑10 timeout, the effect stays applied and the run ends Completed with partial side effects (§18).

  - After MR review, a compensation runs under the original approval or mandate, even after that approval was used or expired, and only restores values recorded for an effect this run applied (invariant 2, RUN‑06).

  - Either way, a compensation that would unlock, open, disarm, turn off a camera, widen access or send outside the trusted boundary needs its own approval (RUN‑06).

  - A paid write's reservation also covers its declared compensation's worst case, so a compensation never waits for budget; that part is released when the run ends without needing it (BUD‑03). The write's grant also covers its declared compensation, only to reverse an effect the run applied and outside the volume limit (CON‑02).

- Request states: pending, blocked, invalid, accepted, rejected, stale and expired, when the expiry passes before the request is decided (RUN‑04).

- Delegates. A delegate's approval executes with the queue owner's token. The delegate must pass the item's visibility check and the approver authority check (§5.9), and the audit record names the queue owner as the user and the delegate as the approver (CON‑07, §18.1).

## 5.5 Beta actions

| Action | Duplicate prevention (RUN‑07) | Recovery (RUN‑06) | Impact tier (RUN‑04) | Approver access check (CON‑12, ASG‑25) | Spike S3 confirms |
| --- | --- | --- | --- | --- | --- |
| Update a row in a named Excel table | (b) If-Match on the row, else (c) a correlation column | Compensable: restore prior values | Low: a restorable overwrite | Edit access to the workbook, read with the approver's own token (spike S9) | If-Match support; formula handling |
| Create or update a SharePoint list item | (c) for creates; (b) or (c) for updates | Compensable: delete or restore | Low | Edit permission on the list item, from SharePoint's effective permissions for the approver (spike S9) | ETag support; read-after-write lag |
| Create or update a ticket in the partner system | (a) if the system enforces idempotency keys, else (c) | Compensable: close as created in error, or restore fields | Low | The ticketing system's own permission check, with the approver's credential (spike S9) | Idempotency support |
| Draft a reply in the user's mailbox | (c) a correlation ID in an extended property | Compensable: delete the draft | Low: a draft isn't a send | Access to the queue owner's mailbox; for a personal mailbox, usually only the owner passes (spike S9, §18) | Filtering on the extended property; Reply-To behavior |

A batch that would change more than 10 rows or items is split (§5.4).

- AI disclosure (SEC‑14). Everything in the beta that people read says it comes from an AI agent acting for a named person, and carries the agent ID (MR‑04): reply drafts (a visible note at the top, in the tenant's wording, plus a message header), ticket bodies, approval-request notifications, and the AI-written narrative in snapshots. The header-only form for drafts the user sends waits on MR review.

- Labels (CON‑11). Each write and draft records the tenant's beta default label on its effect, its lineage and its approval screen (§8.2). Collicity never relabels a target, since that would be a security change SEC‑16 refuses in the beta, and never writes marking text outside the field allowlist; drafts carry the marking in their AI note. Whether a field write into a lower-labeled workbook, list or ticket counts as a downgrade needs the product owner's ruling (§18).

## 5.6 Deprovisioning (CON‑06)

- A deprovisioning signal (a WorkOS directory event or an admin suspension; after MR review, also a disabled account found by the optional directory poll) commits one transaction:

  - the person is suspended and their epoch bumped;

  - their grants and connections are revoked;

  - their runs are paused or routed down RUN‑06.

- Through the outbox, the gateway then destroys their sealed tokens and cancels live segments.

- The gateway refuses their calls within seconds of the signal.

Measured from the identity provider, 60 seconds is out of reach through SCIM alone. Microsoft Entra provisions on a cycle of about 40 minutes, and CAE critical events can take up to 15 minutes to propagate. The design therefore:

- measures from receipt of the signal;

- uses CAE, so Graph rejects a disabled user's tokens even before the signal arrives; a CAE challenge on its own only moves the run to Paused: re-authorization, because it doesn't say why access changed;

- lets a tenant allow admin-consented polling of Graph's user delta at least every 30 seconds, under an application permission the tenant admin grants; each disabled account it finds is a deprovisioning signal (CON‑06). Polling is pending MR review (MR‑02) and isn't built for the beta, which relies on SCIM and CAE (§1.1).

## 5.7 Signed agent requests (alpha; CON‑17 to CON‑19)

- Signing. The gateway's outbound HTTP client signs each request to a target system under the spec's Web Bot Auth profile: @authority and signature-agent, plus @method and @path where the destination's profile allows; created, expires 60 seconds later, keyid, a random single-use nonce, and tag="web-bot-auth". Model-provider calls aren't signed.

- Profiles. A versioned profile per destination sets the draft revision and the Signature-Agent form: the working group's dictionary form by default, the older string form where a verifier still needs it. A manifest flag turns signing off for a target that rejects the headers.

- Switch. A global flag and a per-connector flag turn the alpha off without a release. No invariant or master rule depends on it.

- Key custody (open choice, §18).

  - Option A: a non-exportable KMS Ed25519 key (ECC_NIST_EDWARDS25519), with one KMS Sign call per request. Custody is simplest, but every signed call adds a KMS round trip and counts against KMS request quotas.

  - Option B: short-lived keys generated in each gateway task's memory, never persisted, listed in the directory before first use and rotated daily. There is no per-request KMS call, but the directory changes more often.

  - Recommendation: Option A for the beta's low volume, measured in spike S11 and revisited before the GA load test. KMS doesn't rotate asymmetric keys automatically, so a scheduled job creates a new key at least every 90 days, lists it in the directory, switches signing to it, and retires the old one once its signatures have expired (CON‑19).

- Directory. A gateway job builds the JWK Set with each key's proof-of-possession signature and writes it to S3. CloudFront serves it at /.well-known/http-message-signatures-directory on the key-directory hostname (spec §21 asks which), with the right content type and no redirects. The job runs hourly, since the proofs expire, and on every rotation.

- Audit. Each signed call's key ID and nonce go into its audit record (§10).

## 5.8 Phishing-resistant approvals (CON‑21)

- Every decision is authenticated. Each approval, batch gesture, budget raise (BUD‑04), snapshot publication (SEC‑10), step-up and (after MR review) mandate creation or renewal produces an auth_event recording the method and whether it is phishing-resistant. The gateway won't consume an approval whose event isn't.

- Per-gesture WebAuthn (recommended, §18). The approval screen runs a WebAuthn ceremony with user verification. Its challenge is derived from the canonical hashes of the records being approved, so the authenticator signs exactly what the person approves. A batch takes one touch.

- IdP assertions. For Enterprise, an approving session the IdP asserts as phishing-resistant (Entra's authentication strength, or amr values for FIDO2 or Windows Hello; Okta's equivalents) can stand in for the ceremony. Whether WorkOS passes these claims through is spike S10, and how recent the assertion must be is a design choice (§18).

- Enrollment. Home users use AuthKit passkeys. Enterprise users register a Collicity passkey at their first approval, unless the IdP route works.

- Never accepted: SMS or email codes, email links, and push notifications that only ask to tap Yes.

- Mobile (GA). Approval keys live in the Secure Enclave or StrongBox and require user verification on every use (PLT‑03). Approvals from notifications and while offline are pending MR review.

## 5.9 Approver authority (ASG‑25)

- The check. When a person decides an approval, the gateway runs the connector's declared access check (CON‑12) with the approver's own delegated token, for the action's resource and operation, and checks any role the action needs (ADM‑01). The approver's identity is used only to read their access; the action runs under the queue owner's token.

- Its path. Access checks run outside any run, so the gateway gives them their own path: no step grant, authorized by the approver's own decision, which reads only their own access, with a zero-cost model. Invariant 2 names only the precheck (ASG‑21) as an authorization for access checks, so it needs to name the approver's decision too (§18).

- Other approvers. A budget owner raising a limit (BUD‑04) is checked by role and budget ownership, with no connector call. Budget raises and snapshot publications (SEC‑10) also produce an auth_event and need phishing-resistant authentication (§5.8).

- Connections. Delegates must therefore have connected the beta's connectors themselves, under their own consent (CON‑08). The approval screen asks them to connect before their first approval (§18).

- Caching. A result is cached for at most 5 minutes per approver, resource and operation, and recorded in approver_check and the audit log. At consumption, the gateway checks only that the approver is still active (CON‑06 epochs), not their access again (§18).

- Failure. A failed or incomplete check refuses the approval and offers to route the request to the queue owner or a delegate who passes.

- Per action: §5.5 lists each beta action's check; spike S9 confirms each one.

# 6. Budgets and ledger

Every billable operation reserves its worst case before it starts, against every applicable account in one transaction. The reservation then settles to the actual cost.

## 6.1 Accounts

- Accounts:

  - organization, user and assignment, per period (BUD‑01; BUD‑06 without groups in the beta);

  - the run itself, for the per-run cap;

  - a workspace budget (BUD‑11) for work not charged to an assignment: Q&A (QA‑01–03), "Write this for me" (ASG‑02) and dry runs (ASG‑05). It sits under the user budget, or the account cap in Home; from GA, chat has its own budget at the same level (QA‑04, BUD‑11).

- Money is stored as integer micro-USD, and each reservation records its price-catalog version (BUD‑08).

- Lock order. Rows are always locked in the same rank order: organization, group (GA), user, assignment, workspace or chat (GA), run.

## 6.2 Reserve, start, settle, expire

reserve() is one PL/pgSQL call:

SELECT id FROM ledger_account WHERE id = ANY($accounts)

ORDER BY lock_rank, id FOR UPDATE;

-- if any account has spent + reserved + $amount > limit:

--   return that account (BUD-04 routes the request to its owner) and reserve nothing

UPDATE ledger_account SET reserved = reserved + $amount WHERE id = ANY($accounts);

INSERT INTO reservation (..., state => 'active', expires_at);

INSERT INTO ledger_entry (...);

| State | Meaning | On expiry |
| --- | --- | --- |
| active | Reserved, not yet dispatched | Released |
| started | The gateway is about to dispatch, or has | Charged in full, then reconciled against provider usage where the provider reports it (BUD‑03) |
| settled | Actual cost recorded | — |

- Overruns. An actual cost above its reservation is a guardrail event, because it means the cost model is wrong.

- Batch reservations last at least 24 hours.

- Worked example. Sonnet 5.5 with 10,000 input tokens, 8,000 of them written to a 5-minute cache, and max_tokens of 2,000: $0.020 input + $0.004 cache-write premium + $0.020 output = $0.044 reserved.

- Compute reserves its maximum duration × rate, and the Lambda timeout is the hard stop.

- Estimates (BUD‑02).

  - The first estimates come from dry-run actuals, then from trailing medians per task and model.

  - Each task's max_tokens is set from its 99th-percentile output, so worst-case reservations don't pause runs needlessly near a limit.

  - Gate 1 needs 80% of runs within ±25% of their estimate.

## 6.3 Authorization and alerts

- Paused runs (BUD‑04). A paused run shows what was spent, what remains, the blocking account and the estimate to finish. Only that account's controller can raise it, either once or permanently. Each raise is recorded as a limit_change row and audited; nothing increases automatically.

- Alerts (BUD‑05). Thresholds fire once per period per account, in-app, by email and by browser push in the beta, and to Slack, Teams or webhooks through incoming-webhook URLs that the gateway calls (allowlisted hosts). Defaults: notify at 50%, 80% and 95%; pause at 100%.

- Scale path. One reservation holds its row locks for well under a millisecond, which is enough for hundreds of reservations a second on one organization row; spike S5 measures it. If contention appears: pre-allocated budget chunks per user, or TigerBeetle behind the same interface.

# 7. Models: router, supervisor, inventory

The router starts every task type on a curated default and moves to cheaper models only as verified evidence accumulates. Every check writes evidence, and the evaluation set measures what the checks miss.

## 7.1 Router

- Eligibility (RTR‑01). Admin allow-list ∩ configured providers ∩ capabilities (tools, vision, context, structured output) ∩ the data's classification and residency ∩ retention terms (PRV‑05) ∩ the tenant's compliance profile (SEC‑17). Bedrock cross-region inference is never used, and Claude Platform on AWS calls pin inference_geo to the tenant's region (MR‑07). If the compliance profile alone leaves no eligible unit, the step waits for a person (Waiting: person, SEC‑17); otherwise a step with no eligible unit fails (RTR‑02).

- Selection (RTR‑02). The routable unit is a model version at an effort level. Among eligible units, pick the lowest ĉ / p_LB among those whose lower bound clears the task's quality bar, with priors per RTR‑07.

- Fallback.

  - With priors capped at 10 pseudo-attempts, a strong prior of 0.9 is Beta(9, 1), whose 5th percentile is about 0.72.

  - A model therefore needs roughly 20 consecutive verified successes to clear a 0.9 bar, and more from a 0.5 prior.

  - Until one clears the bar, each task type uses a curated default model with full supervision (every check runs on every attempt, SUP‑02). This is the beta's "rule-based router" (RTR‑02).

  - If the default isn't eligible for a task (RTR‑01), the fallback is the eligible unit with the highest lower bound, ties going to the lower estimated cost. With no eligible unit, the step fails before any model call, and the decision record says which condition excluded each model (RTR‑04).

- Records. Each decision records its candidates, scores and a plain-language reason (RTR‑04). Overrides follow RTR‑05. Exploration (RTR‑06) is GA.

## 7.2 Supervisor (SUP‑01 to SUP‑04)

- Deterministic checks come from a typed check library, selected by each task's success criteria (ASG‑06): schema, row counts, totals, referenced IDs exist, citation integrity, not hidden-only. They run first and gate delivery.

- Judging. A judge from a different model family checks grounding. Subjective checks are sampled according to criticality, except under the RTR‑02 fallback, where every check runs on every attempt (SUP‑02).

- Interventions follow SUP‑03's ladder. Each spends from the budget of the work it checks (the assignment budget, or the workspace budget for a dry run; SUP‑03, BUD‑11) and appears on the run timeline.

- Evidence. Every check writes an append-only evidence record: class, check ID, result, judge model and version, and input hashes.

## 7.3 Inventory and evaluation (INV‑01–03, 06, 07; SUP‑06)

- Inventory.

  - Raw evidence and outcome events are stored; scores are derived from them.

  - Labels stay provisional through the 7-day outcome window. A nightly job then finalizes them and updates posteriors.

  - Attribution follows INV‑07.

- Evaluation set (SUP‑06).

  - Sampling. A sampler draws runs stratified by task type and criticality. For triage it also draws inputs stratified by pipeline stage, including pre-filter drops and mail that matched no trigger.

  - Adjudication. Reviewers who are entitled to the data adjudicate without seeing the supervisor's verdict.

  - Metrics. Recall uses the stratified bootstrap (archived AC‑15); precision counts adjudicated items only (AC‑16).

  - Re-runs. After model or prompt changes, labeled sets are re-run through the Batches API, at half price.

## 7.4 Injection screening (SEC‑13)

Screening runs in the beta, because inbound mail from outside senders is the beta's main injection surface. It is a signal that raises risk, never a grant.

- Inputs. Each intake item's model view goes to a classifier from a different model family than the worker, on Bedrock, chosen in spike S7. untrusted adds deterministic checks, including fuzzy matching for scrambled-word variants of known attack phrases.

- Actions. The supervisor compares each run's tool calls with the task's plan and the owner's request.

- Outputs. Outputs are scanned for credential fingerprints, honeytokens and the canary strings planted in each system prompt.

- Results. Each check writes an evidence record. A positive flags the item on its approval screen, marks the sender (ASG‑17) and sends the item to human review. Screening calls reserve their cost like any model call and are charged to the assignment (BUD‑03).

# 8. Untrusted content, lineage and rendering

Untrusted content is normalized before a model sees it and tracked through everything derived from it. It is rendered so that it can't fetch anything (spec v0.4's hardening: CON‑10, SEC‑11, SEC‑12, ASG‑17; and spec v0.7's second pass: SEC‑13, SEC‑18).

## 8.1 Normalization (CON‑10)

The untrusted library runs only inside extract. It returns a model view, an offset map back to the original, and flags; the original stays in the snapshot.

| Source | Hidden content flagged |
| --- | --- |
| Mail HTML | Text hidden by the CSS cascade (display, visibility, zero size, colour matching the background, off-screen); comments; zero-width characters |
| XLSX | Hidden and very-hidden sheets; hidden rows and columns; ;;; number formats; font colour matching the fill; comments; metadata |
| DOCX | Hidden (vanish) text; comments; tracked deletions; metadata |
| PDF | Invisible render mode; text coloured like its background; text outside the page; metadata |

- Unicode. Text is normalized with NFKC, keeping the offset map. Tag characters and bidirectional controls are stripped and flagged. Mixed-script look-alikes are mapped to their UTS #39 skeleton and flagged (CON‑10).

- Encoded payloads. Base64, hex and URL-encoded runs are decoded, with a depth limit, for inspection. In the model view they are replaced by a flagged placeholder.

- Math markup and look-alike structure. LaTeX or other math markup that renders text invisible is a hidden region. Text that imitates a tool call, tool result, system message or reasoning step is flagged, and the runtime's reserved delimiters are stripped from it (CON‑10).

- Images and media. The beta extracts text only from PDF, DOCX and XLSX and doesn't OCR images, so no image text reaches a model. Image text arrives with GA's vision tasks, under the same flags and screening.

- Macros, scripts and embedded objects are never executed; extract parses files as data (SEC‑15).

- Hidden regions never enter the model view. Reviewers see them with a "hidden in original" marker, and quotes are rendered from the snapshot by offset (SUP‑01).

- Prompt delimiters. Delimiting and labeling untrusted text in prompts is hygiene only, not a control.

## 8.2 Lineage (SEC‑12, SEC‑08)

- Lineage rows. Every artifact (step output, queue item, draft, answer, export) has a lineage row listing its sources, with an untrusted taint. Any untrusted input makes the output untrusted, through later steps, runs and exports.

- Visibility. The same lineage drives visibility. An artifact is visible to the people who can currently read every source in its lineage (SEC‑08), including content pulled in by reads the model initiated.

- Standing instructions are task descriptions, template prompts, assignment versions, builder output, saved chat context and supervisor suggestions.

  - They are read-only to app_worker; app_user may insert drafts.

  - Only accept_version() makes a draft current. It is a SECURITY DEFINER function that requires an interactive session belonging to a person, and its acceptance screen shows provenance.

- Labels (CON‑11). Lineage also carries a sensitivity label. In the beta, every output, draft and snapshot takes the tenant's most restrictive label, or an admin's default that is at least as restrictive; destinations that can't hold a label get a visible marking. The tenant's labels and their order come from Purview through Graph, or an admin enters them (§18).

- Conversations. A Q&A conversation that has cited untrusted content stays tainted for its later turns (SEC‑12).

- Prompt builder. It accepts two types only: TrustedText (from accepted versions) and ModelView (normalized untrusted content). System prompts hold no secrets.

## 8.3 Rendering (SEC‑11)

- Sanitizing. The server sanitizes model output to an allow-listed Markdown tree, and the React renderer never emits remote images, frames or forms.

- Links show their true host. Links to domains outside the tenant's allowlist open through an interstitial; the allowlist is a tenant setting that admins manage (SEC‑11).

- Defense in depth, so that even a sanitizer bug can't fetch anything:

  - Content-Security-Policy: default-src 'self'; img-src 'self' blob: data:; frame-src 'none'; form-action 'self'; base-uri 'none';

  - Trusted Types;

  - Referrer-Policy: no-referrer.

- Math markup is shown as source text, never rendered (SEC‑11).

- Original mail HTML appears only in a sandboxed iframe.

- Exports are escaped against formulas and rendered with networking disabled.

## 8.4 Sender throttling (ASG‑17)

Per-sender counters are checked in the admission transaction:

- by default, items beyond 20 queue items per sender per day go to a review lane;

- bursts of near-duplicate requests are flagged;

- after any rejected, flagged or invalid item, the sender's later items are marked on their approval screens until the queue owner clears the mark;

- the auto-execution cut-off applies once queue mandates exist: after MR review, or in the optional pilot (ASG‑16).

## 8.5 Quarantined reading (SEC‑18)

The design already separates reading from acting: worker holds no credentials and no internet route, and model steps return Pydantic-validated structured output.

- Readers. A model step that reads untrusted content gets no tools beyond its task's declared reads, which the gateway mediates. Anything it proposes becomes an approval request.

- Tool calls. The runtime acts only on structured tool calls in the provider's tool-use format, validated by the gateway against the step's grants, never on text that looks like a tool call.

- Control flow comes only from the accepted version's task graph. Untrusted content fills typed parameters only.

# 9. Visibility, live updates and Q&A

Every read path is bounded by the database: tenant isolation and source visibility are row-level security, not only application checks.

- Tenant isolation (SEC‑09). Every tenant table has FORCE ROW LEVEL SECURITY.

  - Roles: migrator (table owner, CI only), app_user, app_worker and gw. No application role owns a table or has BYPASSRLS.

  - Tenant and person are set per transaction from the authenticated identity, with set_config(…, true). Workers set both the same way.

- Visibility (SEC‑08). Visibility sets are materialized from current source ACLs and recomputed on ACL events and reconciliation. app_user reads content rows through an RLS visibility predicate as well as tenant RLS, so the database itself bounds API reads, Q&A prompt assembly and exports.

- Live updates.

  - Events carry IDs only.

  - The relay assigns each event its per-tenant sequence at publish time; assigning it at insert would skip rows that commit late.

  - Clients resume with SSE's Last-Event-ID and re-fetch details through the API.

- Notifications check visibility at send time, carry no content in their titles, and are dropped for revoked recipients. The client cache is bounded and purged on access.revoked.

- Q&A (QA‑01–03). Answers are assembled in app under the asker's RLS, cite run steps, data rows and documents, and carry the lineage taint of what they cite.

- Snapshots (SEC‑10). A published snapshot is a frozen copy with its own access list:

  - it carries the most restrictive label among its sources;

  - questions about it are answered only from its own content;

  - withdrawing it purges recipients' caches;

  - publish, view, flag and withdrawal are audited.

# 10. Audit log

Every connector call is audited twice: once as intent, before any token is released, and once as result. The log is tamper-evident without ever holding payloads.

- Storage.

  - An audit schema on the same Aurora cluster. Every role gets INSERT only, and a trigger rejects UPDATE and DELETE.

  - Aurora's three-zone durability gives RPO 0 if a zone fails. Losing the whole region is a GA disaster-recovery item (spec §17).

- Contents. Identifiers and hashes only, never payloads or prompt text (SEC‑07):

  - intent and result for every connector call, with the agent ID (MR‑04) and, while the alpha is on, the signature's key ID and nonce (CON‑07);

  - every model call and data access (MR‑16);

  - denials and approvals, with each approval's authentication event and approver check (CON‑21, ASG‑25) and its batch ID;

  - budget authorizations;

  - admin changes and version acceptances;

  - revocations and kill-switch use;

  - snapshot events;

  - share events: offers, acceptances, declines, withdrawals, departures, precheck results and access requests.

- Personal fields are encrypted with per-person data keys, which are themselves wrapped by the tenant's audit key. Search uses blind indexes (keyed hashes, HMAC), stored per person outside the hash chain. Crypto-shredding deletes the wrapped key and the person's blind-index entries; the chain still verifies, and erasure is complete once backups older than the deletion expire (SEC‑07).

- Hash chain (ADM‑07).

  - The sealer appends (tenant, chain_seq, record_id, prev_hash, hash) over the encrypted fields.

  - Every hour a KMS-signed chain head is written to S3 under Object Lock.

  - The chain is verified daily.

  - Monthly partitions are archived as Parquet under Object Lock for 1–7 years.

- Security monitoring (ADM‑06, beta without SIEM export). The admin console's activity feed, policy denials and anomaly alerts read the audit log. Alerts cover unusual volume, new destinations, repeated denied calls, and repeated screening positives or hidden-content flags from one sender, source, user or assignment.

- Master-rule detection (spec §19). Each master rule has a detection query over the gateway log, the audit log and the run, effect and payment records. A scheduled job runs them all and feeds the master-rule guardrail; a rule without a query counts as failing, never as zero.

# 11. Intake

The beta's intake reuses the archived compliance-assistant plan v3.1 design; this table maps it onto Collicity.

| v3.1 concept | Collicity |
| --- | --- |
| source_object, source_version, deduplicated on (tenant, connector, scope, source_id, version) | Same tables. The version is a hash of the normalized message, because Graph's change key changes when mail is read or flagged. IDs come from Prefer: IdType="ImmutableId". Copies of a message in more than one scope are matched by a hash of the normalized message, sender and sent time, never by the sender-chosen Internet Message-ID that v3.1 used as content_identity (RUN‑02, §18.1) |
| Capture before checkpoint, outbox, 410 resync, reconciliation, sync gaps | One intake workflow per scope and per assignment or instance, under its owner's token: notifications only wake it, and the delta query does the reading. Daily reconciliation also refreshes current_acl |
| mail_auth, sender_identity, identity confidence | Only the Authentication-Results header stamped by the tenant's own Microsoft 365 boundary is trusted. ASG‑15 levels apply. Low-confidence mail goes to the review lane and never triggers a run |
| Deterministic pre-filter, suppression floor | The header-only trigger evaluator (monitored folder, sender rule, ASG‑17 counter). The floor forces human review |
| Triage → synthesis | The intake run (§4.2) |
| Obligation | queue_item, with the §18.1 lifecycle. assignment_status and repair_status are separate fields; v3.1 already kept assignment status apart (§18.1) |
| Proposal states | approval_request, with v3.1's states plus expired and a new action kind |
| content_flags | The model view excludes hidden regions and stripped characters; reviewers see markers |
| Stage-outcome strata, 90-day retention | The SUP‑06 sampler, including pre-filter drops |

Supported beta inputs follow §18.1:

- the user's own mailbox, and shared mailboxes they can read;

- selected folders, within a 90-day monitored window;

- attachments up to 10 MB (PDF, DOCX, XLSX);

- English only.

Graph change-notification subscriptions exist only for mail triggers an accepted version declares, so renewing them needs no new approval (MR‑15). Each item's model view is screened before triage (SEC‑13, §7.4).

# 12. Data model

| Area | Tables | Columns that carry the invariants |
| --- | --- | --- |
| Tenancy and identity | tenant, principal, group, role_grant, compliance_profile | home_region; principal.status, kind (person or service), epoch, idp_subject; the regimes that apply and the models, regions and connectors they allow (SEC‑17) |
| Standing instructions | assignment, assignment_version, version_acceptance | agent_id (MR‑04); immutable task graph, grants, budgets, manifest pins, content hash, taint; accepted_by (a person; per instance for a shared assignment, and always its owner); widening diff |
| Connectors | connector_manifest, connection, vault.token, step_grant, capability_usage | Signed manifest (action classes, recovery and duplicate-prevention classes, resource parameters, cost model, replay window, hosts, access check); bound tid/oid and consented scopes; ciphertext readable only by gw; grant expiry and epochs; used ≤ limit |
| Execution | run, run_step, trigger_event, effect, repair_item | state, state_version, segment_no, continuation, price_version; unique dedup key with expiry; unique idempotency key, params_hash, class, outcome (sending, applied, unknown, failed, compensated), prior values |
| Approvals | approval_request, approval_batch, auth_event, approver_check, webauthn_credential | kind (action or compensation) and, for a compensation, its effect_id; canonical parameters and hash; both base versions; bound compensation; impact tier; visibility set; state (including expired); expires_at while undecided and valid_until once decided; consumed_at; batch ID; the authentication method and whether it is phishing-resistant; the approver check's result and source; each person's passkeys (credential ID, public key, sign count) |
| Intake and queue | source_object, source_version, scope_sync, sync_gap, queue_item, evidence_link, review_decision, sender_counter | current_acl; identity confidence, content flags, references to the model view and offset map, stage outcome; item status, assignment_status, repair_status, approved fields, revisions |
| Lineage and visibility | lineage, visibility_set, visibility_member, sensitivity_label | Sources, taint and label_id; the RLS predicate for app_user; each tenant's labels with their name, rank and whether one is the beta default (CON‑11) |
| Budget | ledger_account, reservation, ledger_entry, limit_change, price_version | Limit, spent, reserved, lock rank, alerts sent; reservation state |
| Models and quality | model_catalog, router_decision, model_call, evidence_record, attempt, adjudication | Provider terms (retention, zero data retention, region); labels provisional until the outcome window closes |
| Audit and outbox | audit.record, audit.seal, audit.anchor, person_key, outbox_event, detection_run | INSERT-only; chain hashes; sequence assigned at publish; visibility set; each master-rule detection query's last run and findings |
| Efficiency (G6) | time_study_sample, hands_on_event | Request type and complexity; week 0 or beta; minutes by stage (intake, review, approval, correction, repair); completed or not |
| Agent signing (alpha) | signing_key | Public key, thumbprint, state (pending, active, retired), not-before and not-after. Private keys are never stored here |
| Mandates (pending MR review; the optional pilot) | mandate, mandate_execution | Owner, assignment, actions and targets, bounds and caps, expiry and state; each execution's bounds check, receipt and undo window |
| Sharing (GA) | report_share, assignment_share, assignment_instance, access_check, access_request | Report share: version, recipients, source scopes, label ceiling, state (active, held, withdrawn). Instance: owner is the recipient; state (offered, blocked, active, ended with a reason); accepted and offered versions; personal-selector resolutions; triggers with their own webhook endpoint, verified without displaying a secret; budget account. Access check: requirement, result, the principal that ran it (always the recipient). Access request: route, filed as, approved by, state, expiry, the version scope it applies to |

Retention and deletion (SEC‑04). Retention jobs enforce the spec's §15 data-class table:

- connector payloads are kept for the run plus 7 days, or 90 days for discarded items and the evaluation set;

- prompts and model outputs, 30 days by default;

- derived metadata is pseudonymized when a person is removed;

- audit records follow §10.

A person's export and deletion requests run per class.

# 13. Repository and environments

apps/web                     Vite + React single-page app (client and admin console)

packages/ui, api-client      React Aria design system; client generated from OpenAPI

python/                      uv workspace

services/                  app, worker, gateway, extract

libs/                      core, db (RLS sessions, Alembic), ledger, grants, broker, llm, router,

supervisor, connectors (graph, partner ticketing), intake, untrusted,

lineage, audit, approvals (batches, CON-21, ASG-25), signing (alpha),

screening (SEC-13), telemetry (G6), detection (master-rule checks)

testing/                   fake Graph, fake ticketing, external receivers, scripted and malicious

model stubs, honeytokens

schemas/                     connector manifest, capability grant, assignment DSL, events (JSON Schema)

infra/terraform              VPC (three egress tiers), Aurora, ECS, Lambda, KMS, S3, CloudFront, WAF,

Network Firewall, Temporal PrivateLink

tests/                       invariants, masterrules, redteam, acceptance, e2e

- Local development. just dev starts Postgres, the Temporal dev server, LocalStack (S3, KMS, Lambda) and the fakes in Docker Compose.

- Environments. dev, staging and prod in the beta region, with prod-eu at GA. Configuration comes from the environment and feature flags, never from code branches.

- CI.

  - Lint and types: ruff, pyright and Biome.

  - Tests: pytest with Hypothesis and testcontainers; Temporal replay tests; Playwright with axe.

  - Security (SEC‑02): Semgrep, Dependabot, gitleaks, Syft SBOMs and cosign signatures.

  - The invariant, master-rule and red-team suites run on every change to a prompt, the model registry or a manifest.

# 14. Build plan

Buy everything that isn't the product, build the enforcement and runtime core thin, and defer anything the Beta column doesn't require.

- Buy:

  - WorkOS and Temporal Cloud;

  - AWS managed services: Aurora, ECS Fargate, Lambda, KMS, Secrets Manager, SES, CloudFront, WAF, Network Firewall;

  - Sentry and PostHog;

  - an external AI red team for gate 0;

  - for GA, Vanta or Drata and a penetration test.

- Build thin: the gateway, run engine, ledger, intake, untrusted, the queue UI and the adjudication UI.

- Defer: everything marked Defer in §2, everything pending MR review, and everything the spec postpones (§1.1).

- Lanes: A is platform and execution, B is connectors and intake, C is web.

## 14.1 Phase 0 — foundations to gate 0

| WP | Work (requirement IDs) | Lane | Engineer-weeks | Exit evidence |
| --- | --- | --- | --- | --- |
| P0.1 | Terraform with three egress tiers; CI and SEC‑02 scanning; database roles and RLS (SEC‑09); WorkOS SSO and SCIM (ADM‑01); SEC‑01, SEC‑03 | A | 4–5 | Two tenants sign in; cross-tenant and wrong-role tests pass |
| P0.2 | Spikes S1–S11 (§14.4) | All | 4.5–6 | Spike memos; each beta action's duplicate-prevention and recovery class confirmed |
| P0.3 | Fake Graph (mail, delta, 410, Excel, lists, drafts), fake ticketing with one paid action, and external receivers, all with fault injection | B | 3 | Every RUN‑07 failure mode can be triggered |
| P0.4 | Price catalog and ledger (BUD‑01, 03, 08, 10, 11; BUD‑06 without groups); model adapter (PRV‑01, 03, 05; PRV‑02 only for a partner's own cloud) | A | 4 | A call without a reservation is refused; concurrency property tests pass |
| P0.5 | Connector adapters with full CON‑12 manifests; broker with account binding (CON‑01, 04, 08); grant evaluator (CON‑02, 03); CON‑06, 07; effect journal; write-ahead audit and sealer (ADM‑07, SEC‑07); CON‑05 personal credentials only if a partner needs it | B | 7–8 | Red-team cases for every grant element pass; an action without a cost model is refused; the chain still verifies after crypto-shredding |
| P0.6 | extract and untrusted (CON‑10); SEC‑15 in its v0.7 form, so extract parses and never executes | C | 3–4 | 100% of the CON‑10 corpus flagged |
| P0.7 | Run engine: segments, §7.6 states, ASG‑09–11, 13; RUN‑01–09 in the beta's v0.7 form (15-minute validity, compensation approvals, priority admission of approved actions, impact tiers, honest status, no spawning); the gateway's check of tool calls against the task's plan (SEC‑13, MR‑23); epochs; deprovisioning | A | 8.5–10 | Fault injection: 0 duplicates for classes (a)–(c). After deprovisioning: no calls within 10 s; runs paused within 60 s |
| P0.8 | Web shell (PLT‑01 web, PLT‑06): React Aria design system, approval card, run timeline (ASG‑12), SSE resync, SEC‑11 renderer and CSP | C | 4–5 | An action approved end to end; a poisoned item makes 0 cross-origin requests |
| P0.9 | Thin end-to-end slice; invariant suites; the 26 master-rule release tests and detection queries; injection suite with honeytokens and the injection incident runbook (SEC‑02); external red team | All | 6–8 | Gate 0 report |
| P0.10 | Approvals: phishing-resistant authentication (CON‑21, §5.8); approver authority, with each beta action's CON‑12 access check (ASG‑25, §5.9) | C+A | 5–7 | An approval from a non-phishing-resistant session is refused; a delegate without edit access can't approve; the MR‑11 release tests pass, except the batch cases, which ship with P1.8 and gate it |
| P0.11 | Beta security additions: the default label on every output (CON‑11); AI disclosure on reply drafts (note and header), ticket bodies, approval-request notifications and snapshot narrative (SEC‑14); SEC‑15 in its v0.7 form, so nothing executes; the security class refused (SEC‑16); reader steps without write tools (SEC‑18); the compliance profile and its stop-before-call path (SEC‑17) | B | 4–5.5 | Each requirement's acceptance cases pass; a SEC‑17 fixture stops before the call |

Lane A carries the critical path (P0.1, P0.4, P0.7). Lane C joins it on P0.7's tests once the web shell is done. P0.10 is on the critical path too, because gate 0's master-rule tests need it.

## 14.2 Phase 1 — Enterprise beta to gate 1

| WP | Work (requirement IDs) | Lane | Engineer-weeks | Exit evidence |
| --- | --- | --- | --- | --- |
| P1.1 | Full intake (SCH‑03): subscriptions, resync, reconciliation, sync gaps; ASG‑15; ASG‑17 | B | 6–7 | AC‑07–09 and the ASG‑17 cases pass; soak test on a real tenant |
| P1.2 | Queue domain (ASG‑14, §18.1); visibility RLS and cache purge (SEC‑08); delegates; follow-up mail and merges; lineage (SEC‑12); target lookup (CON‑09) | A+C | 6–7 | AC‑01–06, 10–14 and 17–21 pass |
| P1.3 | Supervisor (SUP‑01–04); router with its fallback (RTR‑01–05, 07); inventory (INV‑01–03, 06, 07) | A | 4–5 | RTR‑04 decision records; posteriors computed |
| P1.4 | Admin console (ADM‑02, 03, 05, 06 without SIEM, 07); budgets UI (BUD‑02, 04, 05); Q&A (QA‑01–03); outline builder (ASG‑01, 02, 04–06); snapshots (SEC‑10) | C+A | 8–10 | A partner admin can onboard without our help |
| P1.5 | SUP‑06 sampler, blind adjudication, recall and precision, guardrail dashboards | B | 3–4 | AC‑15 and AC‑16 pass on seeded data |
| P1.6 | Onboarding; retention, export and deletion (SEC‑04); restore drill (§17); 8 weeks of partner use | All | 2–3, plus the window | Gate 1 report |
| P1.7 | Injection screening in the beta (SEC‑13, §7.4): the classifier, fuzzy screens and output scans; the plan check is in P0.7 | A | 1–2 | Positives flag approval screens and mark senders; false-positive rate reported on benign cases |
| P1.8 | Batch approval (ASG‑11, §5.4), after its MR‑11 self-review | C | 2–3 | A batch of fully shown low-impact actions creates one record each; high-impact and over-10-record batches are refused |
| P1.9 | Efficiency measurement (G6): week-0 time-study protocol and tooling; hands-on-time telemetry on review, approval, correction and repair screens; a sampled time study during the beta; the gate 1 comparison | C+B | 2, plus each partner's week-0 study | Each partner's baseline recorded by request type and complexity before go-live |
| P1.10 | Signed agent requests, alpha (CON‑17–19, §5.7) | B | 1.5–2 | Signatures verify at Cloudflare's test endpoint; the alpha can be switched off |
| P1.11 | Optional mandate pilot (spec §18.1): ASG‑24's controls for queue mandates on one action type with one partner | A+C | 4–6, not counted below | Starts only when all of spec §18.1's conditions hold: the outside re-confirmation of MR‑09 and MR‑11; internal senders only; the action type's compensation cases passing in the partner's tenant; SEC‑13 and every ASG‑24 control live; and the queue owner's opt-in |

## 14.3 Timeline

Collicity is one person today. The table shows the schedule at one, two and three engineers, counted from a full team in week 1, with v0.2's figures in brackets. The target date below allows for hiring.

| Team | Gate 0 | Partners live | Gate 1 |
| --- | --- | --- | --- |
| Three engineers | About week 18–22 (13–15) | About week 29–35 (22–26) | About week 37–43 (30–34) |
| Two engineers | About week 27–33 (18–21) | About week 43–52 (31–36) | About week 51–60 (39–44) |
| One engineer | About week 53–66 (30–35) | About week 84–104 (51–60) | About week 92–112 (59–68) |

These are rough estimates, to be recalibrated after the spikes (P0.2):

- The beta's work grew from about 67–81 engineer-weeks to about 89–111. Most of the growth is CON‑21, ASG‑25, the master-rule tests, the beta security additions and SEC‑13 moving into the beta. The optional mandate pilot adds 4–6 more and isn't counted.

- The three-engineer row is the engineer-week estimate divided by three, which assumes every lane stays busy; it is optimistic. One engineer delivers at most about one engineer-week a week, so the one-engineer row is the estimate in calendar weeks. v0.2's one-engineer row applied a 2.3× factor that assumed more than that, and understated the time.

- The 8-week gate 1 window doesn't scale, and each partner's week-0 time study adds about a week before go-live.

- P1.4 and P1.10 can finish during the window, so they aren't in the time to go-live.

- A solo founder also runs partners, product and sales, so the one-engineer row is a floor, not a forecast.

Target date. The spec sets design partners live by 2027-12-31 and gate 1 by about 2028-03-31, for the founder plus two engineers who join within about three months. With week 1 starting on 2026-10-12, the target falls at about week 64.

- Until the hires join (about week 13), the founder covers the spikes, P0.1 and partner recruiting: about 10 engineer-weeks.

- Each hire's first month runs at about half speed.

- Then, with three engineers, partners go live at about week 39–45. A 25% contingency on build time gives about week 45–53 (August to October 2027), with gate 1 at about week 53–61.

- That leaves about 11 weeks of slack before the target.

- Hiring slips: each month the hires start after about week 13 pushes the dates out by most of a month. One hire instead of two puts partners live at about December 2027 to February 2028, with no slack.

- Recalibrate after the spikes (P0.2) and confirm the date then.

Scope levers (the product owner's call):

- one partner connector instead of two;

- the outline builder, already chosen over a canvas;

- QA‑01–03 and SEC‑10 moved to GA, if the design partners don't need them;

- signed agent requests (CON‑17–19) deferred, since they are alpha and gate nothing (saves 1.5–2 engineer-weeks);

- a minimal compliance profile for the known partners (SEC‑17; saves about 1–1.5);

- batch approval during the gate 1 window rather than before go-live;

- no mandate pilot.

## 14.4 Spikes (weeks 1–3)

| # | What to prove | Fallback |
| --- | --- | --- |
| S1 | Entra consent in partner tenants (admin consent likely needed); account binding; CAE and claims challenges; refresh tokens held outside MSAL's cache | Plain authorization code with PKCE |
| S2 | Deprovisioning latency from Entra and Okta through WorkOS; how fast CAE rejects a disabled user | Rely on CAE and measure from receipt of the signal; polling only after MR review |
| S3 | Per beta action: If-Match on Excel rows and list items; formula handling; filtering on a correlation ID; Reply-To behavior; read-after-write lag; idempotency in the ticketing system | Class (c), or class (d) with approval every time |
| S4 | Temporal segments on ECS: PrivateLink, replay tests, killing a worker and deploying mid-segment | DBOS |
| S5 | Ledger: 500 reservations a second on one organization row, with p99 under 20 ms | Pre-allocated budget chunks per user |
| S6 | untrusted on real partner mail and attachments: hidden-content recall, offset-map round trips, false positives | Conservative "possibly hidden" flags; plain-text part only |
| S7 | Token-counting accuracy against the invoice; refusal path; cache hits with the salt; choosing the Bedrock judge; Batches; availability of Claude Platform on AWS and Bedrock in the beta region | A safety multiplier on reservations |
| S8 | Isolation of extract as a Lambda | One Fargate task per file |
| S9 | Approver authority (ASG‑25): for each beta action, reading an approver's own edit access with their token (Excel workbook, SharePoint list item, the ticketing system), and delegate access to another person's mailbox for reply drafts | Only the queue owner approves that action type |
| S10 | Phishing-resistant assertions (CON‑21): whether WorkOS passes Entra's authentication-strength or amr claims, and Okta's, for the approving session | A WebAuthn ceremony for every approval gesture |
| S11 | Signed agent requests (CON‑17–19): KMS Ed25519 signing latency and request quotas; Cloudflare's test endpoint; the directory's proof signatures | In-memory keys rotated daily, or the alpha switched off |

Week-1 prerequisites:

- two Microsoft 365 E5 test tenants with CAE and shared mailboxes;

- the partner's ticketing system named (still blocking per spec §21);

- the beta region chosen by where the partners need their data;

- each design partner's agreement to a week-0 time study (G6).

## 14.5 GA and Home

Enterprise GA (Phase 2)

- Clients:

  - Tauri desktop, after the Phase 2 decision, and Expo mobile approvals (PLT‑01, 02, 03 approvals; PLT‑05);

  - the Rust edge executor and the on-prem relay.

- Connectors:

  - the connector SDK and custom connectors (CON‑12–15), run in Fargate microVMs whose requests leave through the gateway, which adds credentials on the way out (SEC‑15);

  - labels read from every connector (CON‑11);

  - verifier programs and daily probes for signed requests (CON‑20, alpha);

  - Cedar;

  - the posture-report connectors (Qualys, Splunk, Intune).

- Product:

  - ASG‑03, 07 and 08;

  - after MR review: mandates (ASG‑24), queue mandates with the external-sender policy (ASG‑16), mandate suggestions (ASG‑26) and publishing mandates for recurring report shares (ASG‑19);

  - sharing (ASG‑18–23, §4.5): recurring report shares, per-recipient instances, the access precheck and access requests;

  - BUD‑06 groups, 07 and 09;

  - RTR‑06, SUP‑05 and INV‑04 (SEC‑13 moved into the beta);

  - TPL‑01–07, using Vega-Lite charts and exports rendered with no network access;

  - SCH‑01, 02, 07 and 08; QA‑04–06; ADM‑04 and 08.

- Platform:

  - SIEM export in OCSF format (ADM‑06); PRV‑02 and 04;

  - customer-managed keys through XKS or CloudHSM;

  - the EU cell, using inference_geo;

  - a 10,000-run load test;

  - SOC 2 Type I and a penetration test (SEC‑05).

- After MR review: tiered approval validity, and device-signed approvals from notifications and offline (RUN‑04, PLT‑03); compensations under the original authorization (RUN‑06); the service-account exception and directory polling (CON‑05, CON‑06); approved security and access changes, with two approvers to widen access (SEC‑16); header-only disclosure on drafts the user sends (SEC‑14).

- Postponed for research (SEC‑15): model-written code and queries. Browser automation is out of v1. Nothing in this plan builds them.

Home (Phase 3)

- AuthKit consumer sign-in with passkeys and Sign in with Apple; consumer connectors.

- On-device geofencing (SCH‑04–06; PLT‑04) and a HomeKit module.

- PAY‑01, 02, 04–07, behind gate 3; purchase mandates (PAY‑03), price ceilings (PAY‑05) and home security devices (PAY‑08) after MR review:

  - a separate purchase ledger;

  - approvals signed by a biometric-protected device key (PLT‑03, PAY‑02).

# 15. Verification

Each invariant has its own automated suite that must pass at zero violations; together with the acceptance cases, these suites produce the gate evidence.

| Suite | What it asserts | How |
| --- | --- | --- |
| Invariant 1: permission ceiling | Every out-of-policy call is denied before any token is released, for every grant element; responses are filtered; nothing is retried after a 401 or 403 | Hypothesis generates in-bounds and out-of-bounds pairs against the fakes. The broker's log shows no token for a denied call. Honeytokens in fields that weren't granted never appear downstream |
| Invariant 2: authorization | Every side effect in the fakes' logs joins to an approval with a matching hash, decided through a phishing-resistant authentication event by an approver who passed the authority check. Changed, expired, stale, lapsed (after 15 minutes in the beta) and replayed approvals are denied. Compensating an effect that wasn't applied, or compensating it twice, is always denied. In the beta a compensation also needs its own approval; after MR review, a compensation of an applied, unreversed effect runs under its original approval | Mutation tests; a nightly production join of audit records to approvals, checking both the hash and that the approver is the token's user or a delegate they named, that must find 0 orphans |
| Invariant 3: credentials | No canary token appears in prompts, outputs, logs, traces, Temporal payloads, the database or S3 | Canary tokens issued by a fake identity provider; a fingerprint scanner; IAM and network tests showing worker can't decrypt tokens or reach the internet |
| Invariant 4: budget | Nothing billable runs without a reservation; no limit is exceeded under concurrency, crashes or expiry | Hypothesis stateful tests on Postgres. Every operation billed by the fake model providers, the sandbox or a fake paid connector action (reads, writes and compensations) must join to a reservation, and an action with no declared cost model is refused. Daily reconciliation against provider usage in production |
| Invariant 5 and SEC‑02 | 100% of injection cases blocked; no honeytoken leaves the test sandbox; nothing written to standing instructions | A maintained suite (below) |
| RUN‑07 | 0 duplicates for classes (a)–(c); class (d) pauses | Fakes for each class with faults: lost acknowledgement, timeout before and after commit, crash after sending, read-after-write lag |
| SEC‑11 and SEC‑12 | 0 cross-origin requests when rendering or exporting; taint propagates; writes from worker are denied | Playwright with a network recorder; formula-escaping tests; database permission tests |
| Master rules (spec §19) | Each rule's release test passes, and each detection query finds the violations planted for it | One test module per rule, tagged MR-xx; detection queries replayed over seeded audit data with planted violations |
| Approvals (ASG‑11, ASG‑25, CON‑21) | A batch creates one record per action; high-impact and over-10-record batches are refused; a non-phishing-resistant session can't approve; an approver without access can't approve | Playwright with virtual WebAuthn authenticators; fake IdP tokens with and without phishing-resistant claims; access-check fakes |
| Efficiency (G6) | Telemetry attributes hands-on minutes to the right request and stage | Scripted session replays compared with stopwatch timings |
| Sharing (GA) | A recipient's runs, prechecks and dry runs use only the recipient's tokens and budgets; every run's version was accepted by its owner for its instance; a request filed in a target was approved by the person it was filed as; precheck results reach the owner only for resources the owner can read; an edition with a source outside the confirmed scopes is held | Fixtures with two people and two instances; red-team cases for bait-and-switch versions, probing undeclared resources and request abuse |

The injection suite (invariant 5, SEC‑02)

- It covers the spec's SEC‑02 cases: direct, indirect, encoded, typoglycemia, invisible LaTeX, attachment, image and media, multi-turn (follow-up mail), best-of-N, persona and hypothetical jailbreaks, system-prompt extraction, forged tool results and reasoning steps, and requests to set aside a master rule, each beside similar benign cases. Tool-description poisoning joins at GA with remote MCP servers.

- It grades effects (what the tools did, whether a honeytoken left the sandbox, whether a rule held), never the wording of a reply. It reports false-positive rates on the benign cases and repeats each case.

- It runs against recording stubs, with honeytokens seeded in other folders, columns and mailboxes.

- It runs twice: with a malicious model stub that always obeys the injection, which proves the containment is structural, and nightly with real models.

Acceptance cases and gate evidence

- AC‑01–21 (with AC‑10 and AC‑14 as written in the v3 file) become Given/When/Then pytest scenarios over the fakes with a scripted model. AC‑10, 12 and 13 also run in Playwright.

- The new cases for the action half and for spec v0.4's hardening become AC‑22 to AC‑32:

  - capability violation;

  - lost acknowledgement for each action type;

  - compensation and partial side effects;

  - budget pause and resume;

  - stale and expired approvals;

  - revocation mid-run;

  - snapshot withdrawal;

  - SEC‑11 and SEC‑12;

  - CON‑10 obfuscated and attachment-hidden instructions;

  - ASG‑17.

- Spec v0.17's further cases become AC‑33 to AC‑41: a request to skip an approval or set aside a master rule; an approval whose action or target changed; compensation approvals in the beta (and, after MR review, a compensation under the original approval); forged tool results ignored; the AI disclosure on reply drafts (a visible note in the beta); a step that stops when compliance is uncertain; batch approval limits; approver authority; and phishing-resistant approvals.

- Every test is tagged with requirement IDs, and CI generates the traceability matrix.

- Gate 0 evidence is the CI artifacts plus the red-team report. Gate 1 evidence is the evaluation set plus the guardrail dashboards.

End-to-end check

- Run just dev and seed a tenant.

- Mail the fake mailbox; a queue item appears.

- Approve it in the web UI.

- Confirm that the fake Excel row changes exactly once, the audit chain verifies and the ledger reconciles.

# 16. Technical risks

The riskiest assumptions are tested in the first three weeks (§14.4); each has a fallback that keeps the beta on track.

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Graph write semantics differ from assumptions (If-Match, Reply-To, filtering extended properties) | Duplicate writes or misdirected drafts | Spike S3; class (c) or (d) fallbacks; draft read-back |
| Deprovisioning from Entra takes minutes, not seconds | The 60-second target is missed when measured from the IdP | CAE; measure from receipt of the signal; directory polling only after MR review (MR‑02) |
| Temporal segments behave unexpectedly over PrivateLink or on replay | Runtime rework | Spike S4; DBOS fallback |
| Hot ledger rows | Reservation latency at scale | Spike S5; budget chunks or TigerBeetle |
| Hidden-content detection misses on real mail | An injection reaches the model view | Spike S6; conservative flags; containment doesn't depend on detection (§15) |
| Cost estimates miss ±25% | Gate 1 metric missed; needless pauses | Spike S7; max_tokens set from p99 output; dry runs; a safety multiplier |
| A weak cross-family judge | Low supervisor precision or recall | Choose by labeled-set evaluation; a curated default with full supervision |
| The gateway is a single point of compromise | Credentials and egress sit together | Narrow IAM and KMS policies; Network Firewall allowlist; split the broker out at GA |
| Per-tenant KMS keys at Home scale (Phase 3) | A KMS key costs $1 a month, plus $1 a month for each of its first two rotations; three purpose keys per account cost $3–9 a month, or $300,000–900,000 a month for 100,000 Home accounts | Before Home, revisit SEC‑01's per-tenant keys for Home accounts: one key per account with the purpose in the encryption context, or per-account data keys under shared KMS keys |
| Collicity is one person until the two hires join | Each month they start after about week 13 pushes the dates out by most of a month | Recruit now; until the hires join, the founder covers the spikes, infrastructure and partner recruiting; buy list; scope levers (§14.3) |
| Approver authority can't be read for some beta actions (S9) | Delegates can't approve those actions | Owner-only approval for them (§18) |
| WorkOS doesn't pass phishing-resistant claims (S10) | A passkey ceremony on every approval gesture | One touch per batch; watch its effect on G6 |
| Signing adds latency or hits KMS quotas (S11) | Slower connector calls | In-memory keys, or the alpha switched off |
| WebKitGTK behavior in Tauri (GA) | Desktop parity or accessibility | One-week spike at the start of Phase 2; Electron fallback |

# 17. Spec changes adopted in v0.5

This section is a record of v0.5. Later spec versions changed some of these changes: pre-authorization became mandates (pending MR review), and in the beta each compensation needs its own approval. §1.1 and §18 give the current position.

The product owner approved the 18 changes this document proposed. Spec v0.5 adopts them, refined in an independent review, together with the knock-on edits they needed.

| # | Change | Where it landed in spec v0.5 |
| --- | --- | --- |
| 1 | Refresh tokens are readable only by the token broker in the connector gateway | CON‑04 |
| 2 | At expiry, a reservation that may have started is charged in full, then reconciled where the provider reports usage | BUD‑03; note under the §7.6 table |
| 3 | The deprovisioning bound runs from receipt of the signal; CAE rejects tokens at the target, and a CAE challenge alone means re-authorization; tenants can allow admin-consented directory polling | CON‑06; §17 Revocation row |
| 4 | A workspace budget pays for work charged neither to an assignment nor to chat: Q&A, "Write this for me" and dry runs; from GA, chat has its own budget beside it | New BUD‑11; BUD‑06, BUD‑10, ADM‑02, QA‑04, SUP‑03, §4, §8, §13, §18 matrix |
| 5 | Only Queued and Running runs count against the concurrency cap and queue bound; runs that have executed a step resume without a slot, and runs paused before their first step return to Queued | RUN‑01; §7.6 |
| 6 | Mail is deduplicated by its immutable message ID, never the sender-chosen Message-ID; copies in several scopes are matched by content hash | RUN‑02; §18.1 intake |
| 7 | An expired approval state | RUN‑04; §18.1 acceptance cases |
| 8 | Approvals and pre-authorizations cover declared compensations, even after use, expiry or revocation; a write's grant covers its compensation | Invariant 2; RUN‑06; CON‑02 |
| 9 | When the owner is deprovisioned after effects were applied, the run ends Completed with partial side effects, and a tenant-designated custodian receives its repair items, which rest on the effects and targets (SEC‑08); items no custodian can see are flagged to tenant admins | RUN‑05 and §7.6 (terminal state); RUN‑06, ADM‑01 and §18.1 roles (custodian and flag) |
| 10 | A curated default with full supervision while no model clears the quality bar | RTR‑02; SUP‑02; §9 lead |
| 11 | Assignment and repair status are fields beside the lifecycle | §18.1 lifecycle |
| 12 | Blind indexes for search; crypto-shredding also deletes a person's index entries and completes once older backups expire; audit RPO 0 covers losing a zone | ADM‑07; SEC‑07; §17 Durability row |
| 13 | Look-alikes map to their UTS #39 skeleton; hidden regions stay out of the model view | CON‑10 |
| 14 | A delegate's approval runs with the queue owner's token, and the audit record names both people | CON‑07 (approver field); §18.1 roles |
| 15 | A typed grant evaluator in the beta; Cedar from GA | CON‑02; §16 |
| 16 | First-party connectors run in-process in the beta; MCP at the edges | §6.1 |
| 17 | The decided cloud, stack and team | §5; §16 building blocks and redrawn reference architecture; §20; §21 |
| 18 | A tenant setting for the link-domain allowlist | SEC‑11 |

CON‑14 is unchanged: its "WASM or microVM" already allows the microVM sandboxes that §16 now records.

Spec v0.5 also records the product owner's decision on sharing (§7.7, ASG‑18 to ASG‑23, at GA); §4.5 designs it.

# 18. Gaps, conflicts and design choices

These came up while bringing this design in line with spec v0.17. None is resolved silently: where the design needed an answer to proceed, it records the one it uses and flags it here for the product owner. The spec's own blocking questions (§21: design partners, beta region, target date, database-row keys, runtime defaults, outside recipients on beta snapshots) still stand.

Conflicts inside the spec

| # | Conflict | Where | What v0.3 does | Needs |
| --- | --- | --- | --- | --- |
| 1 | A beta acceptance case expects a compensation under the original approval, but the beta requires each compensation's own approval | Spec §18.1 against §1's interim table and RUN‑06 | Tests compensation approvals in the beta; the original-approval case waits for MR review | Reword the case for the beta |
| 2 | A beta acceptance case expects the AI disclosure in reply-draft headers, but the beta requires a visible note | §18.1 against §1 (MR‑17) and SEC‑14 | Drafts carry a visible note and a header | Reword the case |
| 3 | Two §21 entries still name only "unlocking or disarming" as the home-security hard line | §21: the v0.8 decision record and the open question on hard lines | — | Align with PAY‑08's four actions, if wanted |
| 4 | A beta compliance profile that requires source labels would stop every step, because beta connectors don't read labels | SEC‑17 against CON‑11's beta default | Beta profiles can't require source labels | Decide |
| 5 | RUN‑08 says no summary comes from a model's own account, but Q&A answers history questions in model-written prose | RUN‑08 against QA‑01 | Q&A answers cite run records and never set a status | Say that cited Q&A answers are allowed |
| 6 | The mandate pilot needs an outside re-confirmation during the beta, but the planned reviewer, the penetration tester, comes before GA | §18.1 against §1 and SEC‑02 | P1.11 stays conditional | Line up a design partner's security team if the pilot matters |
| 7 | G6 compares a week-0 time study with beta telemetry, which measure differently | §18.1 and §19 | Also runs a sampled time study during the beta, with telemetry as a cross-check | Confirm the method with the partners |

Gaps and feasibility questions

| # | Gap | Where | What v0.3 does | Needs |
| --- | --- | --- | --- | --- |
| 8 | A delegate usually can't write drafts in the queue owner's personal mailbox, and Graph exposes mailbox delegate permissions poorly, so ASG‑25 may limit reply-draft approvals to the owner | ASG‑25 and §18.1 | Spike S9; fallback: only the queue owner, or delegates on shared mailboxes, approve drafts | Choose the fallback |
| 9 | ASG‑25 needs each delegate's own token, so delegates must connect Graph and the ticketing system themselves; §18.1's roles don't say so | ASG‑25 and CON‑08 | Asks delegates to connect before their first approval | Add to §18.1's roles |
| 10 | The partner ticketing system may have no per-user access check | CON‑12 and ASG‑25 | Spike S9 once the system is named | Choose a system that has one, or owner-only approval |
| 11 | WorkOS may not pass Entra's or Okta's phishing-resistant claims through | CON‑21 | Spike S10; fallback: a WebAuthn ceremony per approval gesture | — |
| 12 | CON‑11's beta default needs the tenant's labels and their order | CON‑11 | Reads Purview labels through Graph, which needs a label-read permission, or lets the admin enter them | Choose |
| 13 | v0.17 doesn't restate what happens when no one approves a compensation in the beta | RUN‑06 interim | Uses v0.7's rule: after the ASG‑10 timeout, the effect stays applied and the run ends Completed with partial side effects | Confirm |
| 14 | Your brief said to postpone "sandboxed custom code", but the spec postpones model-written code and queries and browser automation (SEC‑15); custom connectors still run in a sandbox at GA (CON‑14, spec §16) | SEC‑15 and CON‑14 | Keeps custom connectors at GA, and marks only model-written code, queries and browser automation as postponed | Confirm, or postpone custom connectors too |
| 15 | Labels can't be put on most beta writes: an Excel row carries a label only by relabeling the workbook, which SEC‑16 refuses in the beta; list items and tickets can't hold one; and a snapshot with the tenant's top label may be blocked by SEC‑10's admin label rules | CON‑11, MR‑08, SEC‑10, SEC‑16 | Records the label on the effect, lineage and approval screen; drafts carry it in their AI note (§5.5) | Rule whether a field write into a lower-labeled container is a downgrade |
| 16 | The beta's compensations delete things (a created list item, a reply draft), but §18.1 says deleting records is out of the beta | Spec §18.1 | Treats a compensating delete as a high-impact action with its own approval and delete permission (§5.4) | Say that compensating deletes are allowed in the beta |
| 17 | Invariant 2 names only the precheck as an authorization for access checks, but ASG‑25 runs an access check on every approver | Invariant 2, ASG‑21, ASG‑25 | Authorizes the check by the approver's own decision, on its own gateway path (§5.9) | Add the approver's decision to invariant 2 |
| 18 | SEC‑02's tool-description poisoning cases can't run in the beta, which has no remote MCP servers | SEC‑02, CON‑13 | Adds them at GA; the beta suite has every other case and the incident runbook (§15, P0.9) | — |
| 19 | This design follows spec v0.17, not v0.16 as asked, because v0.17 was published first in the same request; it differs only in naming all four PAY‑08 actions as a hard line | — | Companion to v0.17 | — |

Design choices for the product owner

| # | Choice | Where | What v0.3 recommends |
| --- | --- | --- | --- |
| 20 | Web Bot Auth key custody: a KMS key with a Sign call per request, or in-memory keys rotated daily | CON‑19; spec §16 leaves it to this design | KMS for the beta, measured in spike S11 (§5.7) |
| 21 | Approval authentication: a WebAuthn ceremony per gesture, or an IdP session assertion, and if so how recent | CON‑21 | A ceremony per gesture, bound to the approved hashes, one touch per batch (§5.8); this costs a touch per gesture against G6 |
| 22 | Approver checks cached up to 5 minutes, and not re-run at consumption | ASG‑25 | As stated (§5.9) |
| 23 | Webhook triggers (GA): signed by the sender, or a secret the sender generates and the recipient enters into the vault | ASG‑20 and MR‑03 | Either; Collicity never displays a secret (§4.5) |
| 24 | The screening classifier: the cross-family judge model or a dedicated guard model | SEC‑13 | Chosen in spike S7 (§7.4) |
| 25 | SEC‑17 in the beta: a full compliance profile or a minimal one for the known partners | SEC‑17 | Minimal, as a scope lever (§14.3) |

# Revision history

| Version | Date | Changes |
| --- | --- | --- |
| v0.4 | 2026-10-10 | Follows spec v0.18, which sets the team at three (the founder and two engineers joining within about three months) and the target date: design partners live by 2027-12-31, gate 1 by about 2028-03-31. Adds a two-engineer row, the target-date schedule with hiring time and contingency, and the hiring risk (§1, §14.3, §16) |
| v0.3 | 2026-10-10 | Follows spec v0.17; v0.2 followed v0.5. The beta grows from 82 to 98 named requirement IDs. New: a master-rule map showing what's pending MR review (§1.1); approvals with batches, 15-minute beta validity and compensation approvals (§4, §5.4, §5.5); signed agent requests, alpha (§5.7); phishing-resistant approvals (§5.8); approver authority (§5.9); injection screening in the beta (§7.4); quarantined reading (§8.5); labels, disclosure, honest status, no spawning and the compliance profile; master-rule detection (§10); efficiency measurement (P1.9); new work packages, spikes S9–S11 and a schedule at one engineer and at three (§14); model-written code, queries and browser automation postponed; and the gaps, conflicts and design choices for the product owner (§18) |
| v0.2 | 2026-10-05 | Updated for spec v0.5, which adopts this document's 18 proposed changes: §17 now records where each landed, and cross-references cite the spec instead of proposals. Review findings folded in: per-tenant KMS keys (SEC‑01); the workspace budget (BUD‑11); compensations under pre-authorizations and grants; custodian visibility; resumed runs and the concurrency cap; content-hash matching across scopes; blind-index deletion on crypto-shredding; deprovisioning signals and directory polling; a Home-scale key-cost risk; a design for sharing (§4.5), reworked after an adversarial review of the sharing rules; fixes from a final review: compensations in the write path and tests, reservations for paid connector actions, key purposes and rotation, the chat budget, the router's fallback when the default isn't eligible, human steps inside branches and loops, all BUD‑05 alert channels, suspension versus pause, and re-admitting runs paused before their first step |
| v0.1 | 2026-10-05 | First draft for engineering review: stack review against the specification's defaults; AWS architecture for a team of 1–3; runtime, gateway, ledger and model designs; v0.4 prompt-injection hardening; work-package plan through gate 1 with spikes and a timeline; verification strategy; 18 proposed spec changes |

# Sources

- Collicity — Product Specification (Draft v0.17), and in docs/archive/ the earlier specs, including v0.7 with the master rules' original wording, and the compliance-assistant plans v3 and v3.1 with their acceptance cases.

- Microsoft Entra: develop a SCIM endpoint: provisioning cycles run about every 40 minutes (§5.6).

- Microsoft Entra: continuous access evaluation: critical events, including a disabled user, can take up to 15 minutes to propagate (§5.6).

- Claude Platform on AWS: Anthropic-operated access with SigV4 authentication and AWS billing (§2).

- Claude pricing and prompt caching: model prices and cache-write premiums used in the worst-case formula (§2, §6.2).

- Token counting: exact input counts for reservations (§3.2).

- RFC 8785, JSON Canonicalization Scheme: canonical approval hashes (§3.2).

- Unicode Technical Standard #39: confusable skeletons for look-alike characters (§8.1).

- AWS KMS pricing: $1 per key per month, and $1 a month more for each of a key's first two rotations (§16).

- Temporal: activity definition, idempotency: idempotency is enforced by the service being called (§4.3).

- IETF: HTTP Message Signatures for automated traffic and Cloudflare: Web Bot Auth: the signing profile and key directory (§5.7).

- AWS KMS Sign: Ed25519 signing with ECC_NIST_EDWARDS25519 keys (§5.7).

- W3C Web Authentication: the ceremony behind per-gesture approvals (§5.8).

- Microsoft Entra: authentication strengths: phishing-resistant MFA as a Conditional Access requirement (§5.8).